## Cover & Pricing
HelloSpoke — HubSpot CRM Implementation
v3 SOW Project Sheet · 2026-05-07
Engagement Summary
Client | HelloSpoke
Sayer Lead | Cameron Taggart (deal owner) · Kyle Harbuck (scope/delivery)
Engagement Type | HubSpot CRM Implementation — configuration, automation, UX, enablement
Source CRM | Salesforce (contract expires October 2026)
Target CRM | HubSpot Sales Hub Professional + Commerce Hub Professional
Timeline | 12 weeks
Rate | $175/hr
Median Hours | 164
Median Investment | $28,700
Investment Range | $25,375 (low) – $32,900 (high)
Optional Add-On (QuotaPath) | $2,450 median (decision pending Jeremy 2026-05-08)
Payment Terms | Equal monthly installments of $7,175 over 4 months · Net-15
Tech & Admin Fee | 5% applied to each invoice
Source Call (Rescope) | Fireflies 01KQSVGHKNQ1PM7X5ZPWJ4GJJK · 2026-05-04 walkthrough
Decisions Log | HelloSpoke_decisions.md (5/4 + 5/7 entries)
Supersedes | 4/24 proposal (anchor $44,000) and Gamma deck erumqig7pyx7rhm
Phase Reweighting
Phase | Weeks | Workstreams | Median Hours
Phase 1 — Foundation + Audit | Wk 1–4 | W1, W2, W3 | 46
Phase 2 — Build | Wk 5–9 | W4, W5, W6, W7, W8 | 80
Phase 3 — Enable + Go-Live | Wk 10–12 | W9, W10 | 22
Cross-phase | All | PM | 16
TOTAL | 12 weeks |  | 164

## Workstream Hours
# | Workstream | Low | Median | High | Low $ | Median $ | High $ | Phase
W1 | HubSpot Foundational Architecture | 14 | 18 | 22 | 2450 | 3150 | 3850 | Phase 1
W2 | Data QA + Pre-Production Audit | 14 | 18 | 22 | 2450 | 3150 | 3850 | Phase 1
W3 | Sales Stage Definitions + Gating | 8 | 10 | 14 | 1400 | 1750 | 2450 | Phase 1
W4 | Quoting & CPQ Workflow (Commerce Hub) | 20 | 24 | 30 | 3500 | 4200 | 5250 | Phase 2
W5 | DocuSign Replacement Evaluation + Setup | 4 | 6 | 12 | 700 | 1050 | 2100 | Phase 2
W6 | Automations & Workflows | 16 | 20 | 26 | 2800 | 3500 | 4550 | Phase 2
W7 | Reporting & Dashboards | 14 | 18 | 24 | 2450 | 3150 | 4200 | Phase 2
W8 | ClickUp Workflow Refinement | 8 | 12 | 16 | 1400 | 2100 | 2800 | Phase 2
W9 | Training & Enablement | 10 | 12 | 16 | 1750 | 2100 | 2800 | Phase 3
W10 | UAT & Go-Live | 8 | 10 | 14 | 1400 | 1750 | 2450 | Phase 3
PM | Project Management | 12 | 16 | 20 | 2100 | 2800 | 3500 | Cross-phase
| TOTAL (raw sum) | 128 | 164 | 216 | 22400 | 28700 | 37800
| PROPOSAL RANGE (tightened) | 145 | 164 | 188 | 25375 | 28700 | 32900
QP | QuotaPath Integration (OPTIONAL — pending 5/8) | 10 | 14 | 18 | 1750 | 2450 | 3150 | Optional

## Task Breakdown
WS | Task ID | Task | Phase | Owner | Est. Hrs (median) | Notes / Dependencies
W1 | ARC-T01 | Validate HubSpot tier (Sales Hub Pro + Commerce Hub Pro requirement) | Phase 1 | Sayer | 2 | Blocker for W4; surface upgrade decision early
W1 | ARC-T02 | Configure standard objects (Companies, Contacts, Deals) | Phase 1 | Sayer | 3 | —
W1 | ARC-T03 | Review + validate custom objects from Jeremy's sandbox | Phase 1 | Sayer | 2 | Sandbox access required
W1 | ARC-T04 | Build sales pipeline with Sara's finalized stages | Phase 1 | Sayer | 3 | Depends on Sara delivering stage definitions wk 1
W1 | ARC-T05 | Configure lead status + lifecycle stage progression | Phase 1 | Sayer | 2 | —
W1 | ARC-T06 | Property strategy + custom property creation (snake_case, group org) | Phase 1 | Sayer | 3 | Archive redundant SF-era properties
W1 | ARC-T07 | Team / permission structure (sales, ops, leadership) | Phase 1 | Sayer | 2 | —
W1 | ARC-T08 | Document architecture decisions in admin playbook | Phase 1 | Sayer | 1 | —
W2 | QA-T01 | Sandbox access + initial inventory (record counts, object coverage) | Phase 1 | Sayer | 3 | Blocker: Jeremy sandbox access
W2 | QA-T02 | Data integrity audit (completeness, dedupe, null rates, formatting) | Phase 1 | Sayer | 4 | —
W2 | QA-T03 | Object/property mapping validation (source → target correctness) | Phase 1 | Sayer | 3 | —
W2 | QA-T04 | Association validation (Contact↔Company↔Deal + custom objects) | Phase 1 | Sayer | 3 | —
W2 | QA-T05 | Custom-object structure review (schema, association labels, pipeline alignment) | Phase 1 | Sayer | 2 | —
W2 | QA-T06 | Error handling + rollback plan documentation | Phase 1 | Sayer | 2 | —
W2 | QA-T07 | Production-push green-light memo to Jeremy | Phase 1 | Sayer | 1 | Closes Phase 1 data side
W3 | STG-T01 | Sales-stage workshop with Sara + Christina | Phase 1 | Joint | 2 | Sara delivers definitions wk 1
W3 | STG-T02 | Build stages in HubSpot pipeline (probabilities, entry/exit criteria) | Phase 1 | Sayer | 2 | —
W3 | STG-T03 | Configure required-field gating: sales → implementation (up to 10 fields) | Phase 1 | Sayer | 2 | —
W3 | STG-T04 | Configure required-field gating: implementation → billing (up to 10 fields) | Phase 1 | Sayer | 2 | —
W3 | STG-T05 | Build stuck-deal HubSpot report for leadership | Phase 1 | Sayer | 2 | —
W4 | CPQ-T01 | Commerce Hub Pro setup + Commerce Hub seat assignments | Phase 2 | Sayer | 2 | Tier validated in W1
W4 | CPQ-T02 | Product library architecture (SKU, pricing rules, groups) | Phase 2 | Sayer | 4 | Tier-priced products require manual creation
W4 | CPQ-T03 | CSV product upload pattern (import + bulk-update by product ID) | Phase 2 | Sayer | 4 | Solves Jeremy's #1 named pain
W4 | CPQ-T04 | Quote template configuration with HelloSpoke branding | Phase 2 | Sayer | 3 | —
W4 | CPQ-T05 | Validation rules for quotes above pricing thresholds | Phase 2 | Sayer | 2 | —
W4 | CPQ-T06 | Approval workflows on quote creation/submission | Phase 2 | Sayer | 2 | —
W4 | CPQ-T07 | Native e-signature configuration on quotes (Dropbox Sign-powered) | Phase 2 | Sayer | 3 | Caps: 25/user/mo Pro, 50/user Enterprise
W4 | CPQ-T08 | Quote-to-deal workflow automation | Phase 2 | Sayer | 2 | Quote acceptance → stage advance + tasks
W4 | CPQ-T09 | Quoting documentation + handoff into W9 training | Phase 2 | Sayer | 2 | —
W5 | SIG-T01 | Decision-support workshop with Jeremy (catalog non-quote signing needs) | Phase 2 | Joint | 1 | Decision deadline aligned with Phase 1 kickoff
W5 | SIG-T02 | If Commerce Hub native: signature delegation rules + branded experience | Phase 2 | Sayer | 3 | Default path; folds into W4 config
W5 | SIG-T03 | If PandaDoc selected: account setup + native integration install | Phase 2 | Sayer | 0 | Alternate; +6 hrs at high end of W5 range
W5 | SIG-T04 | If PandaDoc selected: template migration (top 5 doc types) | Phase 2 | Sayer | 0 | Alternate
W5 | SIG-T05 | Audit trail + signing experience verification | Phase 2 | Sayer | 2 | —
W6 | AUT-T01 | Deal-stage notifications (4 stages min) | Phase 2 | Sayer | 3 | —
W6 | AUT-T02 | Deal-stage task creation on advance | Phase 2 | Sayer | 3 | —
W6 | AUT-T03 | Lifecycle progression: lead → MQL → SQL → opp → customer | Phase 2 | Sayer | 4 | —
W6 | AUT-T04 | Customer-journey: lead capture → company assoc → quote → order → kickoff | Phase 2 | Sayer | 4 | —
W6 | AUT-T05 | Sales ownership routing (round-robin or rule-based) | Phase 2 | Sayer | 3 | —
W6 | AUT-T06 | Stuck-deal alerts to managers | Phase 2 | Sayer | 2 | —
W6 | AUT-T07 | Internal email templates + automated send-on-trigger | Phase 2 | Sayer | 1 | —
W7 | DASH-T01 | Executive dashboard (revenue, pipeline health, conversion, velocity) | Phase 2 | Sayer | 4 | —
W7 | DASH-T02 | Sales rep dashboard (my deals, my activity, my targets, alerts) | Phase 2 | Sayer | 4 | —
W7 | DASH-T03 | Ops dashboard (onboarding, ClickUp status sync, customer health) | Phase 2 | Sayer | 4 | —
W7 | DASH-T04 | Custom views + saved filters per role (4–6 views) | Phase 2 | Sayer | 3 | —
W7 | DASH-T05 | Report templates + scheduled exports | Phase 2 | Sayer | 3 | —
W8 | CLK-T01 | Current state review of Jeremy-built integration | Phase 2 | Sayer | 2 | Validated during W2
W8 | CLK-T02 | Workflow correctness audit (statuses, routing, visibility) | Phase 2 | Sayer | 3 | —
W8 | CLK-T03 | Status alignment (canonical onboarding statuses mirrored in HubSpot) | Phase 2 | Sayer | 3 | —
W8 | CLK-T04 | Gating + handoff rules between sales↔impl↔ops | Phase 2 | Sayer | 2 | —
W8 | CLK-T05 | Who-does-what SOPs for implementation team | Phase 2 | Sayer | 2 | —
W9 | TRN-T01 | Admin training session 1: CRM structure + workflows + reports | Phase 3 | Sayer | 3 | Recorded
W9 | TRN-T02 | Admin training session 2: report building + user management | Phase 3 | Sayer | 2 | Recorded
W9 | TRN-T03 | End-user sales training (pipeline, quoting, dashboard usage) | Phase 3 | Sayer | 3 | Recorded + live Q&A
W9 | TRN-T04 | End-user ops training (onboarding, ClickUp sync, handoffs) | Phase 3 | Sayer | 2 | Recorded
W9 | TRN-T05 | Admin playbook + end-user quick-reference cards | Phase 3 | Sayer | 2 | —
W10 | UAT-T01 | Test scenario design (top 10 sales, 5 ops, 5 reporting) | Phase 3 | Sayer | 3 | —
W10 | UAT-T02 | Test matrix execution + bug triage | Phase 3 | Joint | 3 | —
W10 | UAT-T03 | UAT facilitation with sales + ops users | Phase 3 | Sayer | 1 | —
W10 | UAT-T04 | Go-live cutover + communications plan | Phase 3 | Joint | 1 | Single cutover event; phased = change order
W10 | UAT-T05 | 30-day hypercare (bandwidth allocation) | Phase 3 | Sayer | 2 | Bugs + clarifications only
PM | PM-T01 | Weekly standup facilitation × 12 weeks | Cross-phase | Sayer | 6 | 30 min/week
PM | PM-T02 | Status reporting + governance artifact maintenance | Cross-phase | Sayer | 3 | —
PM | PM-T03 | Stakeholder alignment + escalation handling | Cross-phase | Sayer | 3 | —
PM | PM-T04 | Phase reviews × 3 (kickoff/foundation, build, UAT/go-live) | Cross-phase | Sayer | 4 | —
QP* | QP-T01 | HubSpot deal/property configuration to feed QuotaPath | Optional | Sayer | 4 | Pending Jeremy 5/8
QP* | QP-T02 | QuotaPath account setup + native integration install | Optional | Joint | 3 | HelloSpoke owns QuotaPath subscription
QP* | QP-T03 | Commission rule definition workshop | Optional | Joint | 3 | Sara/leadership input required
QP* | QP-T04 | Sales-engineer alignment session (per Cameron's caveat) | Optional | Joint | 2 | —
QP* | QP-T05 | Validation testing across 1 commission cycle | Optional | Sayer | 2 | —
Per-workstream task-hour totals (verification):
W1 (Architecture): 8 tasks, 18 hrs sum
W2 (Data QA): 7 tasks, 18 hrs sum
W3 (Sales Stages): 5 tasks, 10 hrs sum
W4 (Quoting/CPQ): 9 tasks, 24 hrs sum
W5 (DocuSign): 5 tasks, 6 hrs sum
W6 (Automations): 7 tasks, 20 hrs sum
W7 (Dashboards): 5 tasks, 18 hrs sum
W8 (ClickUp): 5 tasks, 12 hrs sum
W9 (Training): 5 tasks, 12 hrs sum
W10 (UAT/Go-Live): 5 tasks, 10 hrs sum
PM (PM): 4 tasks, 16 hrs sum
QP* (QuotaPath (optional)): 5 tasks, 14 hrs sum

## Phase Matrix
Phase | Weeks | Workstream ID | Workstream | Median Hrs | Description
Phase 1 | Wk 1–4 | W1 | HubSpot Foundational Architecture | 18 | Objects, pipelines, lead status, lifecycle stages, properties, team/permissions
Phase 1 | Wk 1–4 | W2 | Data QA + Pre-Production Audit | 18 | Sandbox review, data integrity, mapping validation, error handling + rollback plan, production-push memo
Phase 1 | Wk 1–4 | W3 | Sales Stage Definitions + Gating | 10 | Workshop, stage build, required-field gating at 2 handoffs, stuck-deal report
Phase 2 | Wk 5–9 | W4 | Quoting & CPQ Workflow (Commerce Hub) | 24 | Product library, CSV upload, quote templates, validation, approvals, native e-sig, quote-to-deal automation
Phase 2 | Wk 5–9 | W5 | DocuSign Replacement Evaluation + Setup | 6 | Decision workshop; Commerce Hub native (default) or PandaDoc (alternate, +hrs)
Phase 2 | Wk 5–9 | W6 | Automations & Workflows | 20 | Up to 12 workflows: deal-stage, lifecycle, customer-journey, ownership, alerts
Phase 2 | Wk 5–9 | W7 | Reporting & Dashboards | 18 | 3 dashboards (exec, sales, ops); custom views; report templates
Phase 2 | Wk 5–9 | W8 | ClickUp Workflow Refinement | 12 | Workflow correctness, gating, status alignment (NOT integration build)
Phase 3 | Wk 10–12 | W9 | Training & Enablement | 12 | Admin + end-user tracks, recorded; admin playbook + reference cards
Phase 3 | Wk 10–12 | W10 | UAT & Go-Live | 10 | Test matrix, UAT facilitation, cutover, 30-day hypercare
Cross-phase | All 12 wks | PM | Project Management | 16 | Weekly standups, status reporting, phase reviews, escalation
Optional | TBD | QP* | QuotaPath Integration | 14 | Decision pending Jeremy 2026-05-08; HubSpot config + integration install + commission rules

## Phase Requirements
Phase | WS | Req ID | Requirement | Category | Status
Phase 1 | W1 | ARC-01 | HubSpot tier validated; Commerce Hub Pro licensing path confirmed | Architecture | Pending
Phase 1 | W1 | ARC-02 | Standard objects (Companies, Contacts, Deals) configured | Architecture | Pending
Phase 1 | W1 | ARC-03 | Custom objects from Jeremy's sandbox reviewed and validated | Architecture | Pending
Phase 1 | W1 | ARC-04 | Sales pipeline built with Sara's finalized stages | Architecture | Pending
Phase 1 | W1 | ARC-05 | Lead status + lifecycle stage progression rules configured | Architecture | Pending
Phase 1 | W1 | ARC-06 | Property strategy implemented (snake_case, group org) | Architecture | Pending
Phase 1 | W1 | ARC-07 | Team + permissions configured (sales, ops, leadership) | Architecture | Pending
Phase 1 | W1 | ARC-08 | Architecture decisions documented in admin playbook | Documentation | Pending
Phase 1 | W2 | QA-01 | Sandbox access granted; initial inventory complete | Data QA | Pending
Phase 1 | W2 | QA-02 | Data integrity audit complete (counts, completeness, dedupe, null rates) | Data QA | Pending
Phase 1 | W2 | QA-03 | Object/property mapping validation complete | Data QA | Pending
Phase 1 | W2 | QA-04 | Association validation complete (Contact↔Company↔Deal + custom) | Data QA | Pending
Phase 1 | W2 | QA-05 | Custom-object structure review complete | Data QA | Pending
Phase 1 | W2 | QA-06 | Error handling + rollback plan documented | Data QA | Pending
Phase 1 | W2 | QA-07 | Production-push green-light memo delivered to Jeremy | Data QA | Pending
Phase 1 | W3 | STG-01 | Sales-stage workshop with Sara + Christina complete | Sales Process | Pending
Phase 1 | W3 | STG-02 | Stages built in HubSpot pipeline (probabilities + entry/exit criteria) | Sales Process | Pending
Phase 1 | W3 | STG-03 | Required-field gating: sales → implementation (up to 10 fields) | Governance | Pending
Phase 1 | W3 | STG-04 | Required-field gating: implementation → billing (up to 10 fields) | Governance | Pending
Phase 1 | W3 | STG-05 | Stuck-deal HubSpot report live for leadership | Reporting | Pending
Phase 2 | W4 | CPQ-01 | Commerce Hub Pro setup + Commerce Hub seat assignments | CPQ | Pending
Phase 2 | W4 | CPQ-02 | Product library architecture configured (SKU, pricing, groups) | CPQ | Pending
Phase 2 | W4 | CPQ-03 | CSV product upload pattern documented and validated | CPQ | Pending
Phase 2 | W4 | CPQ-04 | Quote template configured with HelloSpoke branding | CPQ | Pending
Phase 2 | W4 | CPQ-05 | Validation rules implemented for quotes above pricing thresholds | CPQ | Pending
Phase 2 | W4 | CPQ-06 | Approval workflows configured | CPQ | Pending
Phase 2 | W4 | CPQ-07 | Native e-signature configured on quotes (Dropbox Sign) | CPQ | Pending
Phase 2 | W4 | CPQ-08 | Quote signature volume validated against Pro caps | CPQ | Pending
Phase 2 | W4 | CPQ-09 | Quote-to-deal workflow automation configured | CPQ | Pending
Phase 2 | W5 | SIG-01 | Decision-support workshop with Jeremy complete | Signature | Pending
Phase 2 | W5 | SIG-02 | Replacement direction selected (Commerce Hub native OR PandaDoc) | Signature | Pending
Phase 2 | W5 | SIG-03 | Selected platform configured (delegation, branded experience) | Signature | Pending
Phase 2 | W5 | SIG-04 | Up to 5 templates migrated (PandaDoc path only) | Signature | Conditional
Phase 2 | W6 | AUT-01 | Deal-stage notifications live | Automation | Pending
Phase 2 | W6 | AUT-02 | Deal-stage task creation on advance | Automation | Pending
Phase 2 | W6 | AUT-03 | Lifecycle progression workflows live | Automation | Pending
Phase 2 | W6 | AUT-04 | Customer-journey automation live | Automation | Pending
Phase 2 | W6 | AUT-05 | Sales ownership routing configured | Automation | Pending
Phase 2 | W6 | AUT-06 | Stuck-deal alerts to managers | Automation | Pending
Phase 2 | W6 | AUT-07..12 | Up to 12 workflows total (placeholder for additional) | Automation | Pending
Phase 2 | W7 | DASH-01 | Executive dashboard live | Reporting | Pending
Phase 2 | W7 | DASH-02 | Sales rep dashboard live | Reporting | Pending
Phase 2 | W7 | DASH-03 | Ops dashboard live | Reporting | Pending
Phase 2 | W7 | DASH-04..06 | Custom views + saved filters per role | Reporting | Pending
Phase 2 | W7 | DASH-07 | Report templates configured | Reporting | Pending
Phase 2 | W7 | DASH-08 | Scheduled-export configuration complete | Reporting | Pending
Phase 2 | W8 | CLK-01 | Current state review of Jeremy-built integration complete | ClickUp | Pending
Phase 2 | W8 | CLK-02 | Workflow correctness audit complete | ClickUp | Pending
Phase 2 | W8 | CLK-03 | Status alignment confirmed (canonical statuses mirrored) | ClickUp | Pending
Phase 2 | W8 | CLK-04 | Gating + handoff rules documented | ClickUp | Pending
Phase 2 | W8 | CLK-05 | Who-does-what SOPs documented for implementation team | ClickUp | Pending
Phase 3 | W9 | TRN-01 | Admin training delivered (2 sessions, recorded) | Training | Pending
Phase 3 | W9 | TRN-02 | End-user sales training delivered (recorded + Q&A) | Training | Pending
Phase 3 | W9 | TRN-03 | End-user ops/implementation training delivered | Training | Pending
Phase 3 | W9 | TRN-04 | Admin playbook + quick-reference cards delivered | Documentation | Pending
Phase 3 | W10 | UAT-01 | Test scenarios designed (top 10 sales, 5 ops, 5 reporting) | UAT | Pending
Phase 3 | W10 | UAT-02 | Test matrix executed; bugs logged + triaged | UAT | Pending
Phase 3 | W10 | UAT-03 | UAT facilitated with sales + ops users | UAT | Pending
Phase 3 | W10 | UAT-04 | Go-live cutover complete; comms plan executed | Go-Live | Pending
Phase 3 | W10 | UAT-05 | 30-day hypercare initiated | Hypercare | Pending
Optional | QP* | QP-01 | HubSpot deal/property configuration for QuotaPath data feed | QuotaPath | Pending decision
Optional | QP* | QP-02 | Commission rule workshop + sales-engineer alignment | QuotaPath | Pending decision
Optional | QP* | QP-03 | Validation testing across 1 commission cycle | QuotaPath | Pending decision

## Phase Success Criteria
Phase | # | Success Criterion
Phase 1 — Foundation + Audit (Wk 1–4) | 1 | HubSpot tier validated; Commerce Hub Pro licensing path confirmed
Phase 1 — Foundation + Audit (Wk 1–4) | 2 | Foundational architecture configured (objects, pipelines, lead status, lifecycle, properties)
Phase 1 — Foundation + Audit (Wk 1–4) | 3 | Sandbox audited; production-push green-light memo delivered to Jeremy
Phase 1 — Foundation + Audit (Wk 1–4) | 4 | Sales pipeline live with stages + required-field gating + stuck-deal report
Phase 1 — Foundation + Audit (Wk 1–4) | 5 | Architecture decisions documented in admin playbook
Phase 2 — Build (Wk 5–9) | 1 | Commerce Hub CPQ live with quote templates, approvals, native e-signature on quotes
Phase 2 — Build (Wk 5–9) | 2 | DocuSign replacement live (Commerce Hub native OR PandaDoc per Jeremy's decision)
Phase 2 — Build (Wk 5–9) | 3 | 12 automations live across deal-stage, lifecycle, and customer-journey workflows
Phase 2 — Build (Wk 5–9) | 4 | 3 dashboards live (executive, sales, ops); custom views per role
Phase 2 — Build (Wk 5–9) | 5 | ClickUp workflow refinement complete; status sync verified end-to-end
Phase 3 — Enable + Go-Live (Wk 10–12) | 1 | Admin + end-user training delivered and recorded
Phase 3 — Enable + Go-Live (Wk 10–12) | 2 | UAT executed; bugs triaged and resolved
Phase 3 — Enable + Go-Live (Wk 10–12) | 3 | Go-live cutover complete; communications plan executed
Phase 3 — Enable + Go-Live (Wk 10–12) | 4 | 30-day hypercare initiated

## Risk Register
# | Risk | Severity | Likelihood | Impact | Mitigation | Owner | Status
1 | HubSpot tier insufficient for Commerce Hub CPQ + native signature; upgrade to Commerce Hub Pro may be required | High | Medium | W4 blocks; client-side licensing decision required mid-delivery | Validate tier in W1 kickoff; surface upgrade decision before W4 starts | Sayer | Open
2 | Sandbox access delay — Jeremy must grant Sayer access to HubSpot sandbox before W2 begins | High | Medium | W2 delayed; Phase 1 timeline slips | Open item flagged 2026-05-04; access requested in v3 follow-up email | HelloSpoke | Open
3 | Pre-existing data quality issues in Jeremy-built migration surface during W2 audit | Medium | High | Remediation may exceed 2 audit rounds; further rounds are change orders | W2 limited to 2 audit rounds; surface remediation needs early; client decides remediation scope | HelloSpoke | Open
4 | Native signature volume exceeds Commerce Hub Pro caps (25 sigs/user/mo, pooled) | Medium | Low | Forces Enterprise upgrade or PandaDoc fallback for non-quote docs | Volume validation in W1; tier decision before W4; PandaDoc as fallback if needed | HelloSpoke | Open
5 | DocuSign replacement decision delayed — Jeremy hasn't confirmed Commerce Hub native vs PandaDoc | Medium | Medium | W5 hours land at high end (PandaDoc) vs low end (Commerce Hub native) | Decision deadline aligned with Phase 1 kickoff; v3 hours sized at median assuming Commerce Hub native | HelloSpoke | Open
6 | Sales-stage definitions delivered late — Sara is delivering this week post-validation; W3 build depends on it | Medium | Low | W3 starts late, ripples to W6 dependencies | Sara delivers in week 1 of delivery; if late, W3 slides to Phase 1 end | HelloSpoke | Open
7 | Phase 2 scope creep — Christina noted future ideas will surface 'once we live with the new system' | Medium | Medium | New asks in mid-delivery erode v3 scope | v3 explicitly defers Phase 2 ideas to a follow-on engagement; documented in scope | Sayer | Open
8 | QuotaPath decision changes scope mid-engagement | Low | Medium | If Jeremy decides IN after v3 sends, +14 hrs change order | Surface as explicit checkbox with EOW 2026-05-08 deadline; price impact transparent | HelloSpoke | Open
9 | Tier-priced products incompatible with bulk CSV import (HubSpot platform constraint) | Low | Low | If HelloSpoke uses tier pricing, products created manually | W4 inventory captures tier-pricing structure; if present, manual creation hours added | Sayer | Open
10 | Tight 12-week timeline with Phase 2 carrying 80 hrs | Medium | Medium | Phase 2 risks running long if dependencies slip | Weekly standups; phase-review checkpoints; early flag if Phase 1 deliverables run late | Sayer | Open

## Scope Assumptions
# | Assumption
1 | HubSpot tier: Sales Hub Professional minimum; Commerce Hub Professional minimum for W4. Tier validation in W1; upgrade decisions are client-side licensing matters
2 | Sandbox access granted by Jeremy before W2 begins; sandbox contains current Salesforce + Rev IO data
3 | Jeremy completes Rev IO integration, basic ClickUp deal-won automation, Salesforce data migration, ALN integration. Sayer does NOT build these
4 | QuickBooks integration is OUT (Jeremy declined; financial data lives in Rev IO)
5 | Sara delivers finalized sales-stage definitions in week 1 of delivery
6 | Up to 2 rounds of W2 audit + remediation findings; further rounds are change orders
7 | Up to 10 required fields per gate, 2 gates total in W3
8 | Up to 12 workflows in W6; further or higher-complexity workflows are change orders
9 | Up to 3 dashboards (executive, sales, ops), 5–8 reports per dashboard in W7
10 | Up to 2 admin training sessions + 2 end-user sessions per team in W9
11 | 30-day hypercare in W10 covers bugs and clarifications, not net-new feature requests
12 | No multi-currency quotes in W4
13 | No marketing email nurture flows (out of scope; covered in future engagement per 4/14)
14 | Phase 2 ideas deliberately deferred to a follow-on engagement (Christina's ask, 5/4)
15 | Rate: $175/hr; scope changes require written approval and may impact cost or timeline
16 | All work performed remotely unless otherwise agreed
17 | HelloSpoke maintains required Sales Hub + Commerce Hub licensing throughout engagement
18 | Salesforce contract expiration (October 2026) is the hard deadline for migration completion

## Out of Scope
Item | Reason
Rev IO integration build | Jeremy completed (already syncing every 30 min)
ClickUp integration build (deal-won automation, native integration setup, Make middleware) | Jeremy completed
Salesforce → HubSpot data migration build | Jeremy completed; Sayer audits in W2 only
QuickBooks integration | Jeremy declined; financial data lives in Rev IO
ALN integration | Jeremy completing himself this week
Make middleware | Eliminated with stripped ClickUp integration build
Legacy ClickUp ↔ Salesforce integration | Explicitly out per 2026-04-23; Sayer not responsible for legacy plumbing
Marketing email nurture flows | Out per 2026-04-14
Multi-currency quotes | Out
External BI tool integration for reporting | Out
Net-new HubSpot custom-object schema design | Sayer validates Jeremy's existing schemas; doesn't design from scratch
10DLC training flow | Tracked separately per 2026-04-23
Win-property separate survey flow | Out per 2026-04-23 (80/20 standard flow handles)
Phase 2 ideas surfaced post-go-live | Deferred to follow-on engagement
HubSpot Contracts (general contract signing) | Spring 2026 beta; quote-tied; not relied on in v3

## Open Items
Owner | Item | Due / Status | Type
Sayer (Cameron) | Pricing alignment on $28,700 median before v3 ships to Jeremy | Pre-send blocker | Internal
Sayer (Kyle) | Manually apply v3 changes to authoritative SOW Google Sheet | Pre-send blocker | Internal
Sayer (Kyle) | Mirror authoritative changes into working copy SOW | After authoritative apply | Internal
Sayer (Kyle) | Generate new Gamma deck to supersede erumqig7pyx7rhm | Pre-send blocker | Internal
Sayer (Kyle) | Draft + send v3 follow-up email from kyle@gosayer.com | Final step | Internal
Sayer (Kyle) | Add v3 Project Baseline entry to calibration/calibration.md | After v3 lands | Internal
Jeremy Wiley | Answer on QuotaPath in/out | EOW 2026-05-08 | Client decision
Jeremy Wiley | Confirm DocuSign replacement direction (Commerce Hub native vs PandaDoc) | Before W5 begins | Client decision
Jeremy Wiley | Grant Sayer access to HubSpot sandbox (Salesforce + Rev IO data) | Before W2 begins | Client deliverable
Jeremy Wiley | Confirm Commerce Hub Professional licensing (or upgrade decision) | Before W4 begins | Client decision
Sara Hines | Send finalized sales-stage definitions (post sales-team validation) | Week 1 of delivery | Client deliverable
Christina Edwards | Confirm sales-stage definitions align with current ClickUp setup; Phase 2 ideas deferred | Week 1 of delivery | Client confirmation
Jeremy Wiley | Finalize ALN + QuickBooks integrations himself this week (informational) | Self-paced | Client work (out of Sayer scope)