## Scoping Estimate
Hourly Rate: | 150 | (adjust this cell to recalculate all costs)
Phase | Workstream | Description | Min Hours | Max Hours | Median Hours | Min Cost | Max Cost | Median Cost | Notes / Assumptions | Actual Hours | Actual Cost
Phase 1 | CRM Architecture & Setup | Audit existing instance, user roles, permissions, branding | 8 | 18 | 12 |  |  |  | Existing HubSpot instance reconfiguration for 15-18 users
Phase 1 | Pipeline & Deal Management | Sales funnel redesign, stages, deal scoring, lead definitions | 8 | 18 | 12 |  |  |  | Full redesign, not lift-and-shift from Salesforce
Phase 1 | Contact & Company Management | Custom props, multifamily objects, parent-child, dedup strategy | 12 | 24 | 16 |  |  |  | Up to 25 custom properties, 2 custom objects
Phase 2 | Salesforce Data Migration | Phased migration: inactive -> active -> leads, audit + validate | 16 | 36 | 24 |  |  |  | <50K records assumed; phased with validation between loads
Phase 3 | Rev IO Integration | REST API, custom object, billing->deal sync, webhooks | 24 | 44 | 32 |  |  |  | First-time; telecom billing API; sandbox + production phases
Phase 3 | QuickBooks Integration | Revenue actuals sync, OAuth2 setup, reconciliation logic | 12 | 32 | 20 |  |  |  | Native integration insufficient; custom build for revenue actuals
Phase 3 | CPQ & Quoting (HubSpot CPQ native) | Product library, dual dynamic templates, bulk import (up to 300 lines), parent-child auto-creation w/ dedup, native e-sig, close-won sync | 28 | 52 | 38 |  |  |  | HubSpot CPQ native primary (AI CPQ per Billy's direction); PandaDoc fallback as change order; DocuSign sunset
Phase 3 | QuotaPath Coordination | HubSpot-side data flow: deal props, custom object feed, field mapping | 6 | 14 | 10 |  |  |  | QuotaPath handles own implementation; Sayer handles HubSpot-side config
Phase 4 | Automations & Workflows | Lead routing, stage triggers, follow-up automation, notifications | 10 | 22 | 16 |  |  |  | Up to 10 workflows
Phase 4 | Reporting & Dashboards | Executive dashboards, pipeline, forecasting, actuals vs targets | 10 | 22 | 16 |  |  |  | Up to 2 dashboards with 10+ reports each
Phase 4 | Training & Adoption | 3 sessions: admin, sales reps, ops/bookkeeping | 10 | 24 | 16 |  |  |  | 3 x 1-hour virtual sessions, recorded
Cross | Project Management | Kickoff, weekly syncs, status tracking, change management | 14 | 40 | 22 |  |  |  | ~12% of total; weekly for 14 weeks
TOTAL

## Phase Detail
Phase | Weeks | Req ID | Requirement | Category | Success Criterion | Status
Phase 1: CRM Foundation | Wk 1-4
|  | CRM-01 | Existing HubSpot instance audited and cleaned of legacy configuration | CRM Setup |  | Pending
|  | CRM-02 | User roles and permissions configured for 15-18 users | CRM Setup |  | Pending
|  | CRM-03 | Team structure and ownership rules established | CRM Setup |  | Pending
|  | CRM-04 | Sales pipeline redesigned with stages, entry/exit criteria, required fields | Pipeline |  | Pending
|  | CRM-05 | Deal scoring model configured | Pipeline |  | Pending
|  | CRM-06 | Lead vs. deal vs. account definitions standardized | Pipeline |  | Pending
|  | CRM-07 | Contact and company properties configured for multifamily (up to 25) | Data Model |  | Pending
|  | CRM-08 | Parent-child company associations built | Data Model |  | Pending
|  | CRM-09 | Custom objects created for Rev IO billing and multifamily (up to 2) | Data Model |  | Pending
|  | CRM-10 | Deduplication strategy defined and merge rules established | Data Model |  | Pending
|  | PM-01 | Kickoff meeting completed with timeline and cadence aligned | PM |  | Pending
|  | PM-02 | Weekly status syncs established | PM |  | Pending
|  | PM-03 | Project tracker live with workstream status | PM |  | Pending
Success Criteria:
|  |  | 1. All 15-18 users provisioned with correct roles |  | All 15-18 users provisioned with correct roles
|  |  | 2. Sales pipeline has defined stages with entry/exit criteria |  | Sales pipeline has defined stages with entry/exit criteria
|  |  | 3. Custom objects configured with multifamily properties and parent-child |  | Custom objects configured with multifamily properties and parent-child
|  |  | 4. Dedup strategy documented before any data imports |  | Dedup strategy documented before any data imports
|  |  | 5. Kickoff complete, weekly sync running, project tracker live |  | Kickoff complete, weekly sync running, project tracker live
Phase 2: Salesforce Migration | Wk 3-6
|  | MIG-01 | Salesforce data audit completed — objects, counts, quality | Audit |  | Pending
|  | MIG-02 | Field mapping document created (up to 50 mappings) | Mapping |  | Pending
|  | MIG-03 | Phase A: inactive customers and closed deals imported + validated | Migration |  | Pending
|  | MIG-04 | Phase B: active pipeline imported + validated | Migration |  | Pending
|  | MIG-05 | Phase C: leads and prospects imported + validated | Migration |  | Pending
|  | MIG-06 | Post-migration integrity verified — counts match, no data loss | Validation |  | Pending
|  | MIG-07 | Outdated/low-quality records archived | Cleanup |  | Pending
|  | PM-04 | Scope change process in place for discovered gaps | PM |  | Pending
Success Criteria:
|  |  | 1. Field mapping document exists before any data moves |  | Field mapping document exists before any data moves
|  |  | 2. Inactive data imported and verified — counts match SF |  | Inactive data imported and verified — counts match SF
|  |  | 3. Active pipeline imported with correct stages and owners |  | Active pipeline imported with correct stages and owners
|  |  | 4. Leads imported with quality flags resolved or archived |  | Leads imported with quality flags resolved or archived
|  |  | 5. Integrity check confirms no data loss |  | Integrity check confirms no data loss
Phase 3: Integration & Quoting Build | Wk 5-11
|  | INT-01 | Rev IO REST API connection established with auth and error handling | Rev IO |  | Pending
|  | INT-02 | HubSpot custom object for Rev IO billing created and associated with deals | Rev IO |  | Pending
|  | INT-03 | Rev IO data syncing to HubSpot (accounts, invoices, payments, usage) | Rev IO |  | Pending
|  | INT-04 | Webhook or batch sync operational for ongoing Rev IO flow | Rev IO |  | Pending
|  | INT-05 | QuickBooks OAuth2 authentication configured with token refresh | QuickBooks |  | Pending
|  | INT-06 | Revenue actuals from QB paid invoices syncing to HubSpot deals | QuickBooks |  | Pending
|  | INT-07 | Revenue reconciliation logic defined — source-of-truth rules documented | QuickBooks |  | Pending
|  | INT-08 | QuotaPath HubSpot-side data flow configured | QuotaPath |  | Pending
|  | INT-09 | End-to-end chain tested: Rev IO -> HubSpot -> QuotaPath | QuotaPath |  | Pending
|  | INT-10 | Sync monitoring and error alerting established for all integrations | Monitoring |  | Pending
|  | CPQ-01 | HubSpot CPQ product library configured (up to 50 SKUs: VoIP + Notify + equipment) | CPQ |  | Pending
|  | CPQ-02 | Dual dynamic quote templates (VoIP T&C, Notify/SaaS T&C) plus combined template | CPQ |  | Pending
|  | CPQ-03 | Bulk line-item import for property management quotes (up to 300 lines w/ validation) | CPQ |  | Pending
|  | CPQ-04 | Parent-child property auto-creation from quote lines with dedup logic | CPQ |  | Pending
|  | CPQ-05 | Quote approval workflow with up to 2 tiers (rep self-serve + non-standard routing) | CPQ |  | Pending
|  | CPQ-06 | HubSpot native e-signature live, DocuSign retired, templates migrated (MSA/NDA/SOW) | CPQ |  | Pending
|  | CPQ-07 | Close-won automation: quoted amount syncs to deal amount; close date syncs to signature date | CPQ |  | Pending
|  | CPQ-08 | Closed-won quote handoff to Rev IO billing record creation configured | CPQ |  | Pending
|  | PM-05 | Cross-vendor coordination completed | PM |  | Pending
Success Criteria:
|  |  | 1. Rev IO billing data syncing to HubSpot custom objects via API |  | Rev IO billing data syncing to HubSpot custom objects via API
|  |  | 2. QB revenue actuals appearing on HubSpot deals with reconciliation rules |  | QB revenue actuals appearing on HubSpot deals with reconciliation rules
|  |  | 3. Reps can build standard quotes end-to-end without admin assistance; bulk imports up to 300 lines succeed |  | Reps can build standard quotes end-to-end without admin assistance; bulk imports up to 300 lines succeed
|  |  | 4. HubSpot native e-sig live, DocuSign retired, close-won auto-sync operational |  | HubSpot native e-sig live, DocuSign retired, close-won auto-sync operational
|  |  | 5. QuotaPath pulling commission data — full chain tested |  | QuotaPath pulling commission data — full chain tested
|  |  | 6. All integrations have error alerting and monitoring |  | All integrations have error alerting and monitoring
|  |  | 7. Cross-vendor coordination documented |  | Cross-vendor coordination documented
Phase 4: Enablement & Go-Live | Wk 9-14
|  | ENB-01 | Up to 10 automated workflows deployed | Automation |  | Pending
|  | ENB-02 | Executive dashboard built — pipeline, forecasting, revenue | Reporting |  | Pending
|  | ENB-03 | Sales performance dashboard built — activity, conversion, velocity | Reporting |  | Pending
|  | ENB-04 | Admin training delivered and recorded (Christina + ops) | Training |  | Pending
|  | ENB-05 | Sales rep training delivered and recorded | Training |  | Pending
|  | ENB-06 | Ops/bookkeeping training delivered and recorded | Training |  | Pending
|  | ENB-07 | Workflow quick-reference guides provided per role | Training |  | Pending
|  | PM-06 | Project handoff documentation delivered | PM |  | Pending
Success Criteria:
|  |  | 1. Up to 10 workflows live and firing correctly |  | Up to 10 workflows live and firing correctly
|  |  | 2. Dashboards published with pipeline, forecasting, actuals vs targets |  | Dashboards published with pipeline, forecasting, actuals vs targets
|  |  | 3. All 3 user groups completed recorded training |  | All 3 user groups completed recorded training
|  |  | 4. Christina can manage system without Sayer; role guides delivered |  | Christina can manage system without Sayer; role guides delivered
|  |  | 5. Handoff docs delivered, engagement closed |  | Handoff docs delivered, engagement closed

## Risk Register
# | Risk | Severity | Likelihood | Impact | Mitigation | Owner | Status
1 | Salesforce data quality worse than expected | High | Medium | Migration hours exceed estimate; duplicates propagate | SF data audit in Phase 2 before migration; phased with validation | Sayer + HelloSpoke | Open
2 | Rev IO API limitations or poor documentation | High | Medium | Integration scope increases; custom workarounds needed | API investigation early in Phase 3; sandbox testing first | Sayer | Open
3 | Existing HubSpot instance has legacy config | Medium | Medium | Cleanup adds hours to Phase 1 | Instance audit in Week 1; flag conflicts early | Sayer | Open
4 | HubSpot AI CPQ features unstable or missing functionality | High | Medium | CPQ scope shifts to PandaDoc change order; Phase 3 delays | Validate CPQ capabilities in Phase 3 Week 1 before build; PandaDoc fallback scoped | Sayer + HelloSpoke | Open
5 | QuotaPath deal falls through | Medium | Low | Commission tracking deferred; HubSpot-side config repurposed for internal reporting | HubSpot data flow architecture delivers value regardless | HelloSpoke | Open
6 | Stakeholder availability delays | Medium | Medium | Pipeline design, quoting workshop, and training delayed | Weekly cadence at kickoff; Christina as dedicated liaison | HelloSpoke | Open
7 | QuickBooks revenue reconciliation complexity | Medium | Medium | Discrepancies between QB and HubSpot figures | Define source-of-truth rules in Phase 3; reconciliation dashboard | Sayer | Open
8 | Bulk quote import edge cases (300+ line items) | Medium | High | CPQ import fails for property management deals in production | Early validation harness with HelloSpoke's actual CSVs; clear error UX reviewed with Ryan | Sayer | Open
9 | Salesforce contract timeline pressure | Low | Low | October deadline creates urgency if project slips | 14-week timeline targets August; 2+ month buffer | HelloSpoke | Open
10 | Sales team adoption resistance | Medium | Medium | Reps revert to old workflows or inconsistent CRM usage | Role-tailored training in Phase 4; simplified data entry; deal scoring | HelloSpoke + Sayer | Open
11 | Scope creep from adjacent systems | Medium | High | Elastic/ALN, Campfire, Zendesk get added mid-project | Explicit exclusions documented; formal change order process | Both | Open
12 | Rev IO sandbox webhook limitation | Low | High | Cannot test real-time billing events until production | Plan production cutover in Phase 3; batch sync as interim | Sayer | Open

## Assumptions & Exclusions
Section | Item
Scope Assumptions | HubSpot Sales Hub Professional (or Commerce Hub if required for AI CPQ) with 15-18 paid seats
Scope Assumptions | HubSpot AI CPQ features enabled and production-stable by start of Phase 3
Scope Assumptions | DocuSign sunset by HelloSpoke; HubSpot native e-sig replaces it (no parallel run)
Scope Assumptions | Salesforce data volume under 50,000 records total
Scope Assumptions | Rev IO REST API is accessible with documented endpoints
Scope Assumptions | QuotaPath proceeds with their own implementation in parallel
Scope Assumptions | QuickBooks Online admin access and API credentials provided
Scope Assumptions | Salesforce admin access provided for data audit and export
Scope Assumptions | Up to 25 custom contact/company properties
Scope Assumptions | Up to 2 custom objects (Rev IO billing + multifamily)
Scope Assumptions | Up to 50 field mappings for Salesforce migration
Scope Assumptions | Up to 30 field mappings for Rev IO integration
Scope Assumptions | Up to 50 products in HubSpot CPQ product library
Scope Assumptions | Up to 2 dynamic quote templates (VoIP, Notify SaaS) + 1 combined
Scope Assumptions | Up to 2 quote approval tiers (rep self-serve + Jeremy override)
Scope Assumptions | Bulk quote import supports up to 300 line items per quote
Scope Assumptions | Up to 10 automated workflows
Scope Assumptions | Up to 2 dashboards with 10+ reports each
Scope Assumptions | All work is remote unless otherwise agreed
Out of Scope | Elastic / ALN database integration (future phase)
Out of Scope | Campfire ERP evaluation or integration
Out of Scope | ClickUp-to-HubSpot sync
Out of Scope | Zendesk migration or integration
Out of Scope | Email template design or marketing automation
Out of Scope | Custom HubSpot UI extensions
Out of Scope | Ongoing data sync maintenance post-go-live
Out of Scope | HubSpot licensing costs (client responsibility)
Out of Scope | QuotaPath platform implementation (they handle their own)
Client Responsibilities | Assign project liaison (Christina Edwards)
Client Responsibilities | Provide access: HubSpot, Salesforce, Rev IO, QuickBooks
Client Responsibilities | Provide Rev IO and QuickBooks API credentials + sandbox
Client Responsibilities | Attend weekly syncs and milestone reviews
Client Responsibilities | Deliver dashboard requirements write-up (Jeremy Wiley)
Client Responsibilities | Provide Salesforce data exports and field mapping input
Client Responsibilities | Communicate scope changes through formal process
Open Items | Confirm HubSpot instance tier (Professional vs Enterprise)
Open Items | Salesforce data audit needed to confirm record counts and quality
Open Items | Rev IO API credentials and sandbox access needed
Open Items | Confirm multifamily property data needs custom object or standard associations
Open Items | QuotaPath implementation timeline alignment

## Approach Comparison
Dimension | Full Scope (Recommended) | Reduced Scope (CRM Foundation)
Phases Included | 1-4 (all) | 1-2 only (CRM + Migration)
Total Investment | $42,000 | $22,000
Timeline | 14 weeks | 8 weeks
Requirements Covered | 46 of 46 | 21 of 46
Integrations | Rev IO + QuickBooks + QuotaPath assist | None (Phase 3-4 scoped separately)
CPQ / Quoting | HubSpot CPQ native w/ e-sig, bulk import, dynamic templates | Deferred to follow-on
Salesforce Migration | Included (phased) | Included (phased)
Sales Process Redesign | Included | Included
Reporting | Full dashboards with QB actuals | Pipeline-only dashboards
Training | 3 sessions (admin, sales, ops) | 3 sessions (admin, sales, ops)
Commission Tracking | End-to-end data flow configured | Deferred to follow-on
Risk Level | Medium (integration unknowns) | Low (proven CRM workstreams)
SF Deadline Risk | Low (Aug completion, 2+ mo buffer) | Low (Jul completion, 3+ mo buffer)
Recommendation | RECOMMENDED -- delivers full value and completes integration chain before SF contract end | Choose if budget constrained or API credentials unavailable at kickoff