## Scoping Estimate
Phase | Workstream | Description | Notes / Assumptions | Actual Hours | Actual Cost | Variance
Phase 1 | CRM Architecture & Setup | Audit existing instance, user roles, permissions, branding | Standard HubSpot Professional setup
| Pipeline & Deal Management | Sales funnel redesign, stages, deal scoring, lead definitions | SaaS + VoIP product lines; CPQ decision pending
| Contact & Company Management | Custom props, multifamily objects, parent-child, dedup strategy | SF dedup issues; multifamily domain properties
Phase 2 | Salesforce Data Migration | Phased migration: inactive -> active -> leads, audit + validate | Cash-receipt payout trigger adds design complexity
Phase 3 | Rev IO Integration | REST API, custom object, billing->deal sync, webhooks | Standard setup; no unusual requirements
| QuickBooks Integration | Revenue actuals sync, OAuth2 setup, reconciliation logic | HubSpot CPQ native primary (AI CPQ per Billy's direction); PandaDoc fallback as change order; DocuSign sunset
| CPQ & Quoting (HubSpot CPQ native) | Product library, dual dynamic templates, bulk import (up to 300 lines), parent-child auto-creation w/ dedup, native e-sig, close-won sync | Actuals report depends on Rev.io/QB integration
| QuotaPath Coordination | HubSpot-side data flow: deal props, custom object feed, field mapping | Contacts, companies, deals, activities; includes dedup
| ClickUp ↔ HubSpot Onboarding Integration | HubSpot form replaces ClickUp form; Make middleware pushes to ClickUp custom fields; native integration returns task status to HubSpot deal for sales visibility | Tier B architecture (recommended); up to 15 mapped fields; 28-36 hrs (median 32) @ $150/hr = $4,200-$5,400 (median $4,800); ClickUp Unlimited plan required; Make ~$10-30/mo (HelloSpoke billing)
| Automations & Workflows | Lead routing, stage triggers, follow-up automation, notifications | Deal ID linkage unconfirmed; ERP complexity premium
| Reporting & Dashboards | Executive dashboards, pipeline, forecasting, actuals vs targets | One-directional: QB to HubSpot; ERP premium
| Training & Adoption | 3 sessions: admin, sales reps, ops/bookkeeping | QuotaPath leads; Sayer assist only
Cross | Project Management | Kickoff, weekly syncs, status tracking, change management | 3 training groups + playbooks + SOPs
TOTAL

## Phase Details
Phase | Weeks | Req ID | Requirement | Category
Phase 1: CRM Foundation | Wk 1-4 |  |  |  | Success Criteria:
|  | CRM-01 | Existing HubSpot instance audited and cleaned of legacy configuration | CRM Setup | 1. All 15-18 users provisioned with correct roles |  | All 15-18 users provisioned with correct roles
|  | CRM-02 | User roles and permissions configured for 15-18 users | CRM Setup | 2. Sales pipeline has defined stages with entry/exit criteria |  | Sales pipeline has defined stages with entry/exit criteria
|  | CRM-03 | Team structure and ownership rules established | CRM Setup | 3. Custom objects configured with multifamily properties and parent-child |  | Custom objects configured with multifamily properties and parent-child
|  | CRM-04 | Sales pipeline redesigned with stages, entry/exit criteria, required fields | Pipeline | 4. Dedup strategy documented before any data imports |  | Dedup strategy documented before any data imports
|  | CRM-05 | Deal scoring model configured | Pipeline | 5. Kickoff complete, weekly sync running, project tracker live |  | Kickoff complete, weekly sync running, project tracker live
|  | CRM-06 | Lead vs. deal vs. account definitions standardized | Pipeline
|  | CRM-07 | Contact and company properties configured for multifamily (up to 25) | Data Model
|  | CRM-08 | Parent-child company associations built | Data Model
|  | CRM-09 | Custom objects created for Rev IO billing and multifamily (up to 2) | Data Model
|  | CRM-10 | Deduplication strategy defined and merge rules established | Data Model
|  | PM-01 | Kickoff meeting completed with timeline and cadence aligned | PM
|  | PM-02 | Weekly status syncs established | PM
|  | PM-03 | Project tracker live with workstream status | PM
Phase 2: Salesforce Migration | Wk 3-6 |  |  |  | Success Criteria:
|  | MIG-01 | Salesforce data audit completed — objects, counts, quality | Audit | 1. Field mapping document exists before any data moves |  | Field mapping document exists before any data moves
|  | MIG-02 | Field mapping document created (up to 50 mappings) | Mapping | 2. Inactive data imported and verified — counts match SF |  | Inactive data imported and verified — counts match SF
|  | MIG-03 | Phase A: inactive customers and closed deals imported + validated | Migration | 3. Active pipeline imported with correct stages and owners |  | Active pipeline imported with correct stages and owners
|  | MIG-04 | Phase B: active pipeline imported + validated | Migration | 4. Leads imported with quality flags resolved or archived |  | Leads imported with quality flags resolved or archived
|  | MIG-05 | Phase C: leads and prospects imported + validated | Migration | 5. Integrity check confirms no data loss |  | Integrity check confirms no data loss
|  | MIG-06 | Post-migration integrity verified — counts match, no data loss | Validation
|  | MIG-07 | Outdated/low-quality records archived | Cleanup
|  | PM-04 | Scope change process in place for discovered gaps | PM
Phase 3: Integration & Quoting Build | Wk 5-11 |  |  |  | Success Criteria:
|  | INT-01 | Rev IO REST API connection established with auth and error handling | Rev IO | 1. Rev IO billing data syncing to HubSpot custom objects via API |  | Rev IO billing data syncing to HubSpot custom objects via API
|  | INT-02 | HubSpot custom object for Rev IO billing created and associated with deals | Rev IO | 2. QB revenue actuals appearing on HubSpot deals with reconciliation rules |  | QB revenue actuals appearing on HubSpot deals with reconciliation rules
|  | INT-03 | Rev IO data syncing to HubSpot (accounts, invoices, payments, usage) | Rev IO | 3. Reps can build standard quotes end-to-end without admin assistance; bulk imports up to 300 lines succeed |  | QuotaPath pulling commission data — full chain tested
|  | INT-04 | Webhook or batch sync operational for ongoing Rev IO flow | Rev IO | 4. HubSpot native e-sig live, DocuSign retired, close-won auto-sync operational |  | All integrations have error alerting and monitoring
|  | INT-05 | QuickBooks OAuth2 authentication configured with token refresh | QuickBooks | 5. QuotaPath pulling commission data — full chain tested |  | Cross-vendor coordination documented
|  | INT-06 | Revenue actuals from QB paid invoices syncing to HubSpot deals | QuickBooks | 6. All integrations have error alerting and monitoring
|  | INT-07 | Revenue reconciliation logic defined — source-of-truth rules documented | QuickBooks | 7. Cross-vendor coordination documented
|  | INT-08 | QuotaPath HubSpot-side data flow configured | QuotaPath | 8. HubSpot form captures onboarding data natively; ClickUp form retired
|  | INT-09 | End-to-end chain tested: Rev IO -> HubSpot -> QuotaPath | QuotaPath | 9. Sales reps see onboarding phase on every deal without opening ClickUp
|  | INT-10 | Sync monitoring and error alerting established for all integrations | Monitoring | 10. Canonical onboarding status list documented and in production
|  | CPQ-01 | HubSpot CPQ product library configured (up to 50 SKUs: VoIP + Notify + equipment) | CPQ
|  | CPQ-02 | Dual dynamic quote templates (VoIP T&C, Notify/SaaS T&C) plus combined template | CPQ
|  | CPQ-03 | Bulk line-item import for property management quotes (up to 300 lines w/ validation) | CPQ
|  | CPQ-04 | Parent-child property auto-creation from quote lines with dedup logic | CPQ
|  | CPQ-05 | Quote approval workflow with up to 2 tiers (rep self-serve + non-standard routing) | CPQ
|  | CPQ-06 | HubSpot native e-signature live, DocuSign retired, templates migrated (MSA/NDA/SOW) | CPQ
|  | CPQ-07 | Close-won automation: quoted amount syncs to deal amount; close date syncs to signature date | CPQ
|  | CPQ-08 | Closed-won quote handoff to Rev IO billing record creation configured | CPQ
|  | PM-05 | Cross-vendor coordination completed | PM
|  | CLK-01 | HubSpot onboarding form built and published, replacing the ClickUp form | Form
|  | CLK-02 | Up to 15 HubSpot custom properties configured for onboarding data capture | Form
|  | CLK-03 | Make middleware connected to HubSpot + ClickUp with credentials vaulted | Middleware
|  | CLK-04 | Form-submission-to-ClickUp-task mapping configured for all 15 fields with type coercion and error handling | Middleware
|  | CLK-05 | Native ClickUp ↔ HubSpot integration installed, authorized, and object sync toggles configured | Integration
|  | CLK-06 | HubSpot workflow: deal-stage trigger → ClickUp task creation | Workflow
|  | CLK-07 | ClickUp automation: task-status change → HubSpot deal "onboarding phase" property update | Workflow
|  | CLK-08 | Status-list workshop conducted; canonical values + % complete indicators locked with client ops team | Governance
|  | CLK-09 | Sales-facing HubSpot dashboard card for onboarding-phase distribution live | Reporting
|  | CLK-10 | End-to-end test matrix executed; known-limitation workarounds documented | Validation
Phase 4: Enablement & Go-Live | Wk 9-14 |  |  |  | Success Criteria:
|  | ENB-01 | Up to 10 automated workflows deployed | Automation | 1. Up to 10 workflows live and firing correctly
|  | ENB-02 | Executive dashboard built — pipeline, forecasting, revenue | Reporting | 2. Dashboards published with pipeline, forecasting, actuals vs targets
|  | ENB-03 | Sales performance dashboard built — activity, conversion, velocity | Reporting | 3. All 3 user groups completed recorded training
|  | ENB-04 | Admin training delivered and recorded (Christina + ops) | Training | 4. Christina can manage system without Sayer; role guides delivered
|  | ENB-05 | Sales rep training delivered and recorded | Training | 5. Handoff docs delivered, engagement closed
|  | ENB-06 | Ops/bookkeeping training delivered and recorded | Training
|  | ENB-07 | Workflow quick-reference guides provided per role | Training
|  | PM-06 | Project handoff documentation delivered | PM
Phase 3 — ClickUp Integration: Detailed Task Breakdown with Hours (Tier B recommended architecture)
Req ID | Task | Description | Min Hours | Max Hours | Median Hours | Dependencies
CLK-01 | HubSpot form build | Build HubSpot onboarding form (15 fields); progressive profiling config; embed/hosted URL setup | 3 | 5 | 4 | —
CLK-02 | HubSpot property config | Create/audit up to 15 custom contact/deal/company properties to receive form data | 2 | 3 | 2 | CLK-01
CLK-03 | Make middleware connect | Provision Make account; connect HubSpot + ClickUp with credentials vaulted; test auth flow | 1 | 2 | 2 | —
CLK-04 | Form→ClickUp field mapping | Build Make scenario: HubSpot form-submit webhook → ClickUp task create with 15 mapped custom fields; type coercion; error handling + retry | 6 | 8 | 7 | CLK-01, CLK-02, CLK-03
CLK-05 | Native integration install | Install ClickUp↔HubSpot marketplace app in both directions; authorize; configure object sync toggles | 2 | 3 | 2 | —
CLK-06 | HubSpot workflow (forward) | Workflow: deal-stage trigger → Create ClickUp task action (native) with basic fields as fallback backup to the Make path | 2 | 2 | 2 | CLK-05
CLK-07 | ClickUp automation (return) | ClickUp automation: task-status change → update HubSpot deal "onboarding phase" property; map 5 status values + % complete indicator | 3 | 4 | 4 | CLK-05, CLK-08
CLK-08 | Status-list workshop | 1-hour workshop with Christina/Dalton/Haley to lock canonical status list (Waiting for Survey → In Config → Training Scheduled → Call Fwd → Complete) | 2 | 3 | 2 | —
CLK-09 | Sales dashboard card | Build HubSpot dashboard card showing onboarding-phase distribution across open deals; filter by owner/team | 2 | 3 | 2 | CLK-07
CLK-10 | Test matrix + hypercare | End-to-end test matrix (15+ scenarios); document known-limitation workarounds; 30-day post-launch hypercare | 5 | 6 | 5 | all prior
TOTAL
COST @ $150/hr
Architecture alternatives (see HelloSpoke_clickup_workstream.md for full analysis):
• Tier A (18-24 hrs): Fix existing ClickUp form + native integration only — cheapest, doesn't solve PDF problem at source
• Tier B (28-36 hrs): RECOMMENDED — HubSpot form + Make middleware + native integration (this breakdown)
• Tier C (40-48 hrs): HubSpot form + n8n middleware + native integration — cleaner long-term ownership
Optional add-on: Pipeline Governance / Mandatory Field Gating — 8-14 hrs (median 11) @ $150/hr = $1,200-$2,100 (median $1,650)

## Risk Register
# | Risk | Severity | Likelihood | Impact | Mitigation | Owner | Status
1 | Salesforce data quality worse than expected | High | Medium | Migration hours exceed estimate; duplicates propagate | SF data audit in Phase 2 before migration; phased with validation | Sayer + HelloSpoke | Open
2 | Rev IO API limitations or poor documentation | High | Medium | Integration scope increases; custom workarounds needed | API investigation early in Phase 3; sandbox testing first | Sayer | Open
3 | Existing HubSpot instance has legacy config | Medium | Medium | Cleanup adds hours to Phase 1 | Instance audit in Week 1; flag conflicts early | Sayer | Open
4 | HubSpot AI CPQ features unstable or missing functionality | High | Medium | CPQ scope shifts to PandaDoc change order; Phase 3 delays | Validate CPQ capabilities in Phase 3 Week 1 before build; PandaDoc fallback scoped | Sayer + HelloSpoke | Open
5 | QuotaPath deal falls through | Medium | Low | Commission tracking deferred; HubSpot-side config repurposed for internal reporting | HubSpot data flow architecture delivers value regardless | HelloSpoke | Open
6 | Stakeholder availability delays | Medium | Medium | Pipeline design, quoting workshop, and training delayed | Weekly cadence at kickoff; Christina as dedicated liaison | HelloSpoke | Open
7 | QuickBooks revenue reconciliation complexity | Medium | Medium | Discrepancies between QB and HubSpot figures | Define source-of-truth rules in Phase 3; reconciliation dashboard | Sayer | Open
8 | Bulk quote import edge cases (300+ line items) | Medium | High | CPQ import fails for property management deals in production | Early validation harness with HelloSpoke's actual CSVs; clear error UX reviewed with Ryan | Sayer | Open
9 | Salesforce contract timeline pressure | Low | Low | October deadline creates urgency if project slips | 14-week timeline targets August; 2+ month buffer | HelloSpoke | Open
10 | Sales team adoption resistance | Medium | Medium | Reps revert to old workflows or inconsistent CRM usage | Role-tailored training in Phase 4; simplified data entry; deal scoring | HelloSpoke + Sayer | Open
11 | Scope creep from adjacent systems | Medium | High | Elastic/ALN, Campfire, Zendesk get added mid-project | Explicit exclusions documented; formal change order process | Both | Open
12 | Rev IO sandbox webhook limitation | Low | High | Cannot test real-time billing events until production | Plan production cutover in Phase 3; batch sync as interim | Sayer | Open
13 | ClickUp native integration limitations (2.0/5 marketplace rating; no HubSpot custom object support; custom-field mapping one-direction) | Medium | High | Workarounds add hours; some edge cases require middleware | Middleware (Make) scoped from day 1; document known limitations in SOW | Sayer | Open
14 | ClickUp HubSpot Integration 2.0 on roadmap but unscheduled | Low | Low | Minor rework if breaking change ships mid-delivery | Do not scope against unreleased features; revisit if released during delivery | Sayer | Open
15 | Status list drafting dependency on HelloSpoke ops team | Medium | High | 2-4 hr delivery delay if late | Status-list workshop included in Phase 3 kickoff; client commits to draft before build | HelloSpoke | Open

## Assumptions & Exclusions
SCOPE ASSUMPTIONS
HubSpot Sales Hub Professional (or Commerce Hub if required for AI CPQ) with 15-18 paid seats
HubSpot AI CPQ features enabled and production-stable by start of Phase 3
DocuSign sunset by HelloSpoke; HubSpot native e-sig replaces it (no parallel run)
Salesforce data volume under 50,000 records total
Rev IO REST API is accessible with documented endpoints
QuotaPath proceeds with their own implementation in parallel
QuickBooks Online admin access and API credentials provided
Salesforce admin access provided for data audit and export
Up to 25 custom contact/company properties
Up to 2 custom objects (Rev IO billing + multifamily)
Up to 50 field mappings for Salesforce migration
Up to 30 field mappings for Rev IO integration
Up to 50 products in HubSpot CPQ product library
Up to 2 dynamic quote templates (VoIP, Notify SaaS) + 1 combined
Up to 2 quote approval tiers (rep self-serve + Jeremy override)
Bulk quote import supports up to 300 line items per quote
Up to 10 automated workflows
Up to 2 dashboards with 10+ reports each
All work is remote unless otherwise agreed
ClickUp Unlimited plan or higher (required for custom fields + native HubSpot integration)
Up to 15 custom fields mapped between ClickUp and HubSpot for the onboarding form flow
Make subscription set up under HelloSpoke's account (~$10-30/mo); HelloSpoke owns the billing relationship
Canonical onboarding status list drafted by HelloSpoke before integration build (Sayer facilitates 1-hour workshop)
OUT OF SCOPE
Elastic / ALN database integration (future phase)
Campfire ERP evaluation or integration
Zendesk migration or integration
Email template design or marketing automation
Custom HubSpot UI extensions
Ongoing data sync maintenance post-go-live
HubSpot licensing costs (client responsibility)
QuotaPath platform implementation (they handle their own)
CLIENT RESPONSIBILITIES
Assign project liaison (Christina Edwards)
Provide access: HubSpot, Salesforce, Rev IO, QuickBooks
Provide Rev IO and QuickBooks API credentials + sandbox
Attend weekly syncs and milestone reviews
Deliver dashboard requirements write-up (Jeremy Wiley)
Provide Salesforce data exports and field mapping input
Communicate scope changes through formal process
Provide sales process documentation and playbook content for training
Draft canonical onboarding status list + % complete indicators before integration build (Christina/Dalton/Haley)
Sarah Hines: Share sales-stage definitions with implementation team (committed 2026-04-23)
Dalton Palmer: Provide ClickUp implementation form link for reference during form redesign
Approve Make subscription setup under HelloSpoke billing account
OPEN ITEMS
Jeremy Wiley: Confirm Rev.io deal ID linkage feasibility for invoice-to-deal mapping
Confirm HubSpot instance tier (Professional vs Enterprise)
Salesforce data audit needed to confirm record counts and quality
Rev IO API credentials and sandbox access needed
Confirm multifamily property data needs custom object or standard associations
QuotaPath implementation timeline alignment
Jeremy Wiley: Confirm in/out on the mandatory field gating add-on (optional Workstream)
Jeremy Wiley: Confirm Win-property separate survey flow is out of scope (standard flow handles 80/20)
Confirm ClickUp plan tier is Unlimited or higher (required for integration)