## Overview
Milestone Group — HubSpot CRM Implementation
Client | Milestone Group
Engagement | HubSpot CRM Implementation
Start Date | 2026-04-13
Est. End Date | 2026-06-12
Project Lead | Kyle Harbuck
Project Manager | Weston Baker
Primary Contact | Jason Wise
Weekly Standup | Monday 2:00 PM Central
PHASE TIMELINE
Phase | Name | Dates
Phase 1 | Contacts & Activity Capture | 2026-04-13 → 2026-05-08
Phase 2 | Deal Pipeline & Reporting | 2026-05-11 → 2026-05-22
Phase 3 | Integrations, Training & Go-Live | 2026-05-25 → 2026-06-12
COLOUR LEGEND
Sayer-owned task
Client action required
Shared — both teams involved

## Phase 1
PHASE 1: CONTACTS & ACTIVITY CAPTURE ¦ 2026-04-13 → 2026-05-08
SUCCESS CRITERIA: All 10 users can log in with correct roles and permissions · Parent-child company hierarchy reflects Milestone portfolio structure · Contacts migrated from all sources with <5% duplicate rate · Email and calendar sync working for all users · Auto-contact creation firing on new email/meeting interactions · Task reminders and follow-up workflows triggering correctly
CRM-01 · CRM Architecture & Setup
# | Task | Owner | Status | Target Week | Notes
1 | Review current HubSpot portal access and document baseline state | Sayer | Not Started | Wk 1 (Apr 13–18)
2 | Configure portal name, logo, favicon, timezone, currency, and date format | Sayer | Not Started | Wk 1 (Apr 13–18)
3 | Define user role structure: Admin, Sales Manager, Sales Rep | Sayer | Not Started | Wk 1 (Apr 13–18)
4 | Create user accounts for all 10 users across 4 offices (Atlanta, Dallas, Denver, South Florida) | Sayer | Not Started | Wk 1 (Apr 13–18)
5 | Configure team structure: create teams by office location | Sayer | Not Started | Wk 1 (Apr 13–18)
6 | Configure permission sets per role (contact visibility, deal access, report access) | Sayer | Not Started | Wk 1 (Apr 13–18)
7 | Set up security settings: login notifications, 2FA requirements for admins | Sayer | Not Started | Wk 1 (Apr 13–18)
8 | Establish naming conventions document for properties, lists, and workflows | Sayer | Not Started | Wk 1 (Apr 13–18)
9 | QA: verify all 10 users can log in with correct role and data visibility | Sayer | Not Started | Wk 1 (Apr 13–18)
CRM-02 · Contact & Company Management
# | Task | Owner | Status | Target Week | Notes
1 | Run properties workshop with Jason Wise: map all required custom contact and company fields | Shared | Not Started | Wk 1 (Apr 13–18)
2 | Create custom contact properties (persona, broker type, relationship tier, acquisition focus, etc.) | Sayer | Not Started | Wk 2 (Apr 21–25)
3 | Create custom company properties (entity type, market, PE firm vs. portfolio company, AUM, etc.) | Sayer | Not Started | Wk 2 (Apr 21–25)
4 | Configure lifecycle stages for BD pipeline (prospect → active → closed) | Sayer | Not Started | Wk 2 (Apr 21–25)
5 | Configure lead statuses for pipeline progression | Sayer | Not Started | Wk 2 (Apr 21–25)
6 | Build parent-child company hierarchy (PE firm → portfolio company structure) | Sayer | Not Started | Wk 2 (Apr 21–25)
7 | Set up association labels: broker, lender, investment partner, evangelist, acquisition target | Sayer | Not Started | Wk 2 (Apr 21–25)
8 | Configure persona picklist options: broker, evangelist, investment partner, lender, competitor | Sayer | Not Started | Wk 2 (Apr 21–25)
9 | Configure deduplication detection rules (match on email, phone, name+company) | Sayer | Not Started | Wk 2 (Apr 21–25)
10 | Build active list: acquisition target contacts | Sayer | Not Started | Wk 2 (Apr 21–25)
11 | Build active list: broker contacts by office/territory | Sayer | Not Started | Wk 2 (Apr 21–25)
12 | QA: create 5 sample companies with parent-child relationships and verify associations | Sayer | Not Started | Wk 2 (Apr 21–25)
MIG-01 · Data Migration: Contact Import
# | Task | Owner | Status | Target Week | Notes
1 | Export templates sent to all Milestone team members [✓ Complete — sent Apr 10] | Shared | Not Started | Wk 1 (Apr 13–18)
2 | Receive Outlook contact exports from Jason, Robert, David, Rich, Jim (target: Apr 18, hard deadline: Apr 25) | Client | Not Started | Wk 2 (Apr 21–25)
3 | Receive Zoho CRM export (contacts and associated notes only; other Zoho modules excluded) | Client | Not Started | Wk 2 (Apr 21–25)
4 | Audit received data: record counts per source, field coverage gaps | Shared | Not Started | Wk 2 (Apr 21–25)
5 | Build field mapping matrix: source columns → HubSpot property IDs | Shared | Not Started | Wk 2 (Apr 21–25)
6 | Define duplicate handling rules with Jason Wise (owner priority, cross-office contact logic) | Shared | Not Started | Wk 2 (Apr 21–25)
7 | Define contact ownership assignment rules by office/territory | Shared | Not Started | Wk 2 (Apr 21–25)
8 | Clean and normalize data: standardize company names, phone formats, email validation | Shared | Not Started | Wk 3 (Apr 28–May 1)
9 | Deduplicate in staging: apply ownership rules, flag unresolvable conflicts for manual review | Shared | Not Started | Wk 3 (Apr 28–May 1)
10 | Execute test load: ~500 contacts | Shared | Not Started | Wk 3 (Apr 28–May 1)
11 | Review test load results with Jason Wise: duplicate rate, field mapping, ownership accuracy | Shared | Not Started | Wk 3 (Apr 28–May 1)
12 | Fix mapping or deduplication issues identified in test load | Shared | Not Started | Wk 3 (Apr 28–May 1)
13 | Execute full production import | Shared | Not Started | Wk 4 (May 4–8)
14 | Post-migration QA: verify record count, associations, and owner assignments | Shared | Not Started | Wk 4 (May 4–8)
15 | Deliver migration summary to Jason Wise (record counts, duplicate rate, sources) | Shared | Not Started | Wk 4 (May 4–8)
CRM-05 · Email & Communication Setup
# | Task | Owner | Status | Target Week | Notes
1 | Obtain Microsoft 365 admin credentials from Milestone | Sayer | Not Started | Wk 2 (Apr 21–25)
2 | Configure email tracking domain settings in HubSpot | Sayer | Not Started | Wk 2 (Apr 21–25)
3 | Connect each user's Outlook inbox to HubSpot (10 users, 10 connections) | Sayer | Not Started | Wk 2 (Apr 21–25)
4 | Configure email tracking settings per user (auto-log, open tracking, click tracking) | Sayer | Not Started | Wk 2 (Apr 21–25)
5 | Set up email domain exclusion rules (internal @milestonegroup.com, personal domains) | Sayer | Not Started | Wk 2 (Apr 21–25)
6 | Configure auto-association rules (link emails to contacts and deals automatically) | Sayer | Not Started | Wk 2 (Apr 21–25)
7 | QA: send test emails, verify activity logs appear on contact records | Sayer | Not Started | Wk 3 (Apr 28–May 1)
8 | Document user-by-user connection status and any per-user configuration issues | Sayer | Not Started | Wk 3 (Apr 28–May 1)
INT-02 · Integration: Outlook Calendar & Contact Sync
# | Task | Owner | Status | Target Week | Notes
1 | Configure Outlook Calendar sync in HubSpot (App Marketplace → Microsoft Calendar) | Sayer | Not Started | Wk 2 (Apr 21–25)
2 | Set sync permissions: define which calendar events log to CRM (external meetings only vs. all) | Sayer | Not Started | Wk 3 (Apr 28–May 1)
3 | Configure meeting auto-log rules: attendee matching to HubSpot contacts | Sayer | Not Started | Wk 3 (Apr 28–May 1)
4 | Set up Outlook contact sync rules (HubSpot wins on conflict) | Sayer | Not Started | Wk 3 (Apr 28–May 1)
5 | QA: create test meeting, verify it appears on contact timeline | Sayer | Not Started | Wk 3 (Apr 28–May 1)
6 | Complete per-user calendar sync validation across all 10 users | Sayer | Not Started | Wk 3 (Apr 28–May 1)
7 | Document known limitations: sync latency, contact match rules, known edge cases | Sayer | Not Started | Wk 3 (Apr 28–May 1)
CRM-04 · Automations & Workflows
# | Task | Owner | Status | Target Week | Notes
1 | Workflow requirements session with Jason Wise: confirm all 8 automation use cases | Shared | Not Started | Wk 2 (Apr 21–25)
2 | Workflow 1: Auto-log activity — trigger email/meeting logs on contact records | Sayer | Not Started | Wk 3 (Apr 28–May 1)
3 | Workflow 2: Auto-contact creation — create contact from new Outlook email (with domain exclusions) | Sayer | Not Started | Wk 3 (Apr 28–May 1)
4 | Workflow 3: Follow-up reminder — 30-day no-activity task trigger | Sayer | Not Started | Wk 3 (Apr 28–May 1)
5 | Workflow 4: Domain exclusion filter — suppress @milestonegroup.com and personal email interactions | Sayer | Not Started | Wk 3 (Apr 28–May 1)
6 | Workflow 5: Lead routing — assign owner by office/territory on contact creation | Sayer | Not Started | Wk 3 (Apr 28–May 1)
7 | Workflow 6: Deal stage notification — notify owner when deal advances to a new stage | Sayer | Not Started | Wk 4 (May 4–8)
8 | Workflows 7 & 8: To be defined — confirm use cases with team | Sayer | Not Started | Wk 4 (May 4–8)
9 | QA: test each workflow with sample data (triggers, actions, enrollment criteria) | Sayer | Not Started | Wk 4 (May 4–8)
10 | Fix bugs identified in workflow testing | Sayer | Not Started | Wk 4 (May 4–8)
11 | Document each workflow: trigger logic, actions, and admin contact for changes | Sayer | Not Started | Wk 4 (May 4–8)

## Phase 2
PHASE 2: DEAL PIPELINE & REPORTING ¦ 2026-05-11 → 2026-05-22
SUCCESS CRITERIA: Deal pipeline configured with stage gates enforcing required fields · Multi-party associations working (broker + lender + owner linked to deals) · Executive dashboard showing pipeline status, BD activity, and contact metrics · Sample deals flow through pipeline correctly with all associations intact
CRM-03 · Pipeline & Deal Management
# | Task | Owner | Status | Target Week | Notes
1 | Pipeline design session with Jason Wise: confirm deal stages, required fields, and qualification criteria | Shared | Not Started | Wk 5 (May 11–15)
2 | Create deal pipeline with confirmed stage names (4–6 stages) | Sayer | Not Started | Wk 5 (May 11–15)
3 | Configure required fields per stage (stage gate enforcement) | Sayer | Not Started | Wk 5 (May 11–15)
4 | Create custom deal properties (property type, investment thesis, acquisition target, market, etc.) | Sayer | Not Started | Wk 5 (May 11–15)
5 | Configure deal owner assignment rules | Sayer | Not Started | Wk 5 (May 11–15)
6 | Set up deal views and filters by office/team | Sayer | Not Started | Wk 5 (May 11–15)
7 | Configure multi-party associations: broker, lender, owner, and acquisition target linked to deals | Sayer | Not Started | Wk 5 (May 11–15)
8 | Set up auto-link rules: associate contacts by role when added to a deal | Sayer | Not Started | Wk 6 (May 18–22)
9 | Configure deal close date requirements and stage progression rules | Sayer | Not Started | Wk 6 (May 18–22)
10 | QA: run 3 sample deals through pipeline, verify stage gates enforce required fields | Sayer | Not Started | Wk 6 (May 18–22)
11 | QA: verify multi-party associations work correctly on sample deals | Sayer | Not Started | Wk 6 (May 18–22)
12 | Fix any pipeline configuration issues identified in QA | Sayer | Not Started | Wk 6 (May 18–22)
CRM-06 · Reporting & Dashboards
# | Task | Owner | Status | Target Week | Notes
1 | Reporting requirements session with Jason Wise: confirm dashboard priorities and key metrics | Shared | Not Started | Wk 5 (May 11–15)
2 | BD Activity Dashboard — Report: activity by rep (calls, meetings, emails this week/month) | Sayer | Not Started | Wk 5 (May 11–15)
3 | BD Activity Dashboard — Report: activity by office/territory | Sayer | Not Started | Wk 6 (May 18–22)
4 | BD Activity Dashboard — Report: top reps by contact touches | Sayer | Not Started | Wk 6 (May 18–22)
5 | Contact Engagement Dashboard — Report: lifecycle stage distribution | Sayer | Not Started | Wk 5 (May 11–15)
6 | Contact Engagement Dashboard — Report: contacts with no activity in 30+ days | Sayer | Not Started | Wk 6 (May 18–22)
7 | Contact Engagement Dashboard — Report: contacts created by source (migration vs. organic) | Sayer | Not Started | Wk 6 (May 18–22)
8 | Deal Pipeline Dashboard — Report: pipeline by stage (count) | Sayer | Not Started | Wk 6 (May 18–22)
9 | Deal Pipeline Dashboard — Report: deal age by stage | Sayer | Not Started | Wk 6 (May 18–22)
10 | Deal Pipeline Dashboard — Report: new deals this month by owner | Sayer | Not Started | Wk 6 (May 18–22)
11 | Configure scheduled report email delivery to Jason Wise (weekly digest) | Sayer | Not Started | Wk 6 (May 18–22)
12 | Review all dashboards with Jason Wise: confirm metrics are reading correctly | Sayer | Not Started | Wk 6 (May 18–22)
13 | Adjust reports based on feedback | Sayer | Not Started | Wk 6 (May 18–22)
14 | Document report definitions and how to read each metric | Sayer | Not Started | Wk 6 (May 18–22)

## Phase 3
PHASE 3: INTEGRATIONS, TRAINING & GO-LIVE ¦ 2026-05-25 → 2026-06-12
SUCCESS CRITERIA: Fireflies integration auto-logging transcripts to correct contact records · All admins trained and able to manage properties, workflows, and reports independently · All end users trained across 4 offices including mobile app setup · UAT complete with all critical bugs resolved · Go-live executed with all users active · Documentation delivered: admin guide, end-user guide, mobile quick-start guide
INT-01 · Integration: Fireflies
# | Task | Owner | Status | Target Week | Notes
1 | Confirm Fireflies subscription status and API access with Jason Wise (client action — required before configuration) | Client | Not Started | Wk 7 (May 25–29)
2 | Connect Fireflies to HubSpot: authenticate in Fireflies dashboard | Sayer | Not Started | Wk 7 (May 25–29)
3 | Configure auto-logging rules: define which meetings log to CRM | Sayer | Not Started | Wk 7 (May 25–29)
4 | Configure contact matching logic: match meeting participants to HubSpot records by email | Sayer | Not Started | Wk 7 (May 25–29)
5 | Set up activity note creation: transcript summary auto-created on contact record | Sayer | Not Started | Wk 7 (May 25–29)
6 | Configure meeting type tagging (BD vs. internal, deal-related vs. relationship-building) | Sayer | Not Started | Wk 7 (May 25–29)
7 | QA: run 2–3 test meetings, verify transcripts appear on correct contact records | Sayer | Not Started | Wk 7 (May 25–29)
8 | Validate contact matching edge cases (new contacts, partial email matches) | Sayer | Not Started | Wk 7 (May 25–29)
9 | Document known limitations and troubleshooting steps for admin | Sayer | Not Started | Wk 7 (May 25–29)
TRN-01 · Training: Admin
# | Task | Owner | Status | Target Week | Notes
1 | Identify 1–2 admin champions at Milestone | Sayer | Not Started | Wk 7 (May 25–29)
2 | Build admin training agenda and materials | Sayer | Not Started | Wk 7 (May 25–29)
3 | Training Session 1 (90 min): portal settings, user management, properties, lists | Sayer | Not Started | Wk 7 (May 25–29)
4 | Training Session 2 (90 min): workflows, reports, troubleshooting common issues | Sayer | Not Started | Wk 7 (May 25–29)
5 | Admin Q&A and sign-off: confirm admins can perform key tasks independently | Sayer | Not Started | Wk 8 (Jun 1–5)
TRN-02 · Training: End Users
# | Task | Owner | Status | Target Week | Notes
1 | Build end-user training materials (designed for varying tech comfort, ages 25–65) | Sayer | Not Started | Wk 7 (May 25–29)
2 | Training Session 1 (60 min): daily CRM usage — contacts, activity feed, task management | Sayer | Not Started | Wk 8 (Jun 1–5)
3 | Training Session 2 (60 min): deal pipeline — creating deals, advancing stages, associating contacts | Sayer | Not Started | Wk 8 (Jun 1–5)
4 | Training Session 3 (45 min): mobile app setup and on-the-go workflows | Sayer | Not Started | Wk 8 (Jun 1–5)
5 | Record all sessions for async reference and future new-hire onboarding | Sayer | Not Started | Wk 8 (Jun 1–5)
6 | Collect training feedback from attendees | Sayer | Not Started | Wk 8 (Jun 1–5)
UAT-01 · UAT & Go-Live
# | Task | Owner | Status | Target Week | Notes
1 | Create UAT test scripts covering all configured workstreams (CRM-01 through INT-01) | Shared | Not Started | Wk 7 (May 25–29)
2 | Share test scripts with Jason Wise and Robert Strong before UAT session | Shared | Not Started | Wk 8 (Jun 1–5)
3 | UAT Session 1: power users (Jason, Robert) — walk through test scripts, log issues | Shared | Not Started | Wk 8 (Jun 1–5)
4 | Triage bugs from Session 1: classify as critical / high / low | Shared | Not Started | Wk 8 (Jun 1–5)
5 | Fix critical and high-priority bugs from Session 1 | Shared | Not Started | Wk 8 (Jun 1–5)
6 | UAT Session 2: full team (all offices) — role-specific flows and general walkthrough | Shared | Not Started | Wk 8 (Jun 1–5)
7 | Fix remaining critical bugs from Session 2 | Shared | Not Started | Wk 8 (Jun 1–5)
8 | Kyle Harbuck sign-off: UAT complete | Sayer | Not Started | Wk 8 (Jun 1–5)
9 | Jason Wise sign-off: UAT complete | Client | Not Started | Wk 8 (Jun 1–5)
10 | Execute go-live: confirm all users active, send go-live announcement to Milestone team | Shared | Not Started | Wk 8 (Jun 1–5)
11 | Hypercare Week 1: daily monitoring, user questions, fix adoption blockers | Shared | Not Started | Wk 8 (Jun 1–5)
12 | Hypercare Week 2: monitor usage, close out remaining open items | Shared | Not Started | Wk 9 (Jun 8–12)
DOC-01 · Documentation & SOPs
# | Task | Owner | Status | Target Week | Notes
1 | Create admin reference guide (settings, user management, workflow editing, troubleshooting) | Sayer | Not Started | Wk 7 (May 25–29)
2 | Create end-user daily workflow guide (logging activity, managing contacts, advancing deals, tasks) | Sayer | Not Started | Wk 8 (Jun 1–5)
3 | Create mobile quick-start guide (app download, setup, key mobile actions) | Sayer | Not Started | Wk 8 (Jun 1–5)
4 | Create CRM hygiene guide: weekly review process (contact cleanup, deal updates, task completion) | Sayer | Not Started | Wk 8 (Jun 1–5)
5 | Deliver all documentation to Jason Wise in shared Google Drive data room | Sayer | Not Started | Wk 8 (Jun 1–5)