## Project Plan
Phase | Stage | Week(s) | Task | Owner | Status | Notes
Phase 1 | Foundation | 1-2 | Project kickoff meeting | Sayer + AB Team | Not Started
Phase 1 | Foundation | 1-2 | NetSuite data audit (SKU quality, duplicates) | Sayer | Not Started | SuiteQL queries
Phase 1 | Foundation | 1-2 | Product catalog extraction from NetSuite | Sayer | Not Started | ~700 SKUs
Phase 1 | Foundation | 1-2 | HubSpot CPQ module configuration | Sayer | Not Started | Commerce Hub setup
Phase 1 | Foundation | 1-2 | NetSuite OAuth 2.0 M2M credential setup | Sayer + NetSuite Team | Not Started | API access required
Phase 1 | Foundation | 1-2 | Kuebix API credential validation | Sayer + Sarah-Beth | Not Started | Basic Auth
Phase 1 | Foundation | 3-4 | Product catalog loaded into HubSpot | Sayer | Not Started | Custom properties, bulk load
Phase 1 | Foundation | 3-4 | NetSuite integration active (customer data sync) | Sayer | Not Started | Credit status, payment terms
Phase 1 | Foundation | 3-4 | Quote approval workflows configured | Sayer | Not Started
Phase 1 | Foundation | 4 | Milestone review with Mike and Patrick | Sayer + Leadership | Not Started | Foundation checkpoint
Phase 1 | Integration | 5-6 | Weight engine: Dorm Mattress module | Sayer | Not Started | HIGH complexity -- 180+ paths
Phase 1 | Integration | 5-6 | Weight engine: Camp Mattress module | Sayer | Not Started | MEDIUM complexity -- 48 paths
Phase 1 | Integration | 5-6 | Weight engine: Dura-Last module | Sayer | Not Started | LOW-MEDIUM -- 12 paths
Phase 1 | Integration | 5-6 | Kuebix freight integration operational | Sayer | Not Started | Multi-carrier LTL rate shopping
Phase 1 | Integration | 5-6 | Origin warehouse routing configured | Sayer | Not Started | Map all shipping origins
Phase 1 | Integration | 5-6 | Quote template design (draft) | Sayer + Sarah-Beth | Not Started | Branding and layout
Phase 1 | Integration | 7-8 | Weight engine: SoFlux + Vinyl modules | Sayer | Not Started | LOW complexity
Phase 1 | Integration | 7-8 | Quote template finalized | Sayer + Sarah-Beth | Not Started | Matching NetSuite format
Phase 1 | Integration | 7-8 | Volume discount + tax automation | Sayer | Not Started | 10% volume, state-based tax
Phase 1 | Integration | 7-8 | Payment terms logic (prepay/net 10/30/60) | Sayer | Not Started | Credit hold integration
Phase 1 | Integration | 7-8 | Quote-to-order bridge tested | Sayer | Not Started | HubSpot quote to NetSuite Estimate
Phase 1 | Integration | 8 | Milestone review with leadership | Sayer + Leadership | Not Started | Integration checkpoint
Phase 1 | Launch | 9-10 | End-to-end integration testing | Sayer | Not Started | All three systems
Phase 1 | Launch | 9-10 | UAT sessions with Caleb and Don | Sayer + Sales Team | Not Started | 2 sessions planned
Phase 1 | Launch | 9-10 | Bug fix window | Sayer | Not Started
Phase 1 | Launch | 9-10 | Training: Sales team (Caleb, Don) | Sayer | Not Started | Recorded sessions
Phase 1 | Launch | 9-10 | Training: Admin team (Sarah-Beth, Patrick) | Sayer | Not Started | Recorded sessions
Phase 1 | Launch | 11-12 | Go-live cutover | Sayer + AB Team | Not Started
Phase 1 | Launch | 11-12 | Hypercare monitoring (2 weeks) | Sayer | Not Started | Integration flows, freight, templates
Phase 1 | Launch | 12 | Admin guide + user reference card delivered | Sayer | Not Started
Phase 1 | Launch | 12 | Phase 1 close-out | Sayer + Leadership | Not Started | Go/no-go for Phase 2
Phase 2 | Hardening | 13-14 | Production API setup (Railway) | Sayer | Not Started | CI/CD, monitoring, logging
Phase 2 | Hardening | 13-14 | Weight engine migration to production API | Sayer | Not Started | All 5 modules + shared utilities
Phase 2 | Hardening | 13-14 | Unit test coverage for weight calculations | Sayer | Not Started | Cell-by-cell validation
Phase 2 | Hardening | 13-14 | Regression testing against Phase 1 baseline | Sayer | Not Started
Phase 2 | Hardening | 15-16 | Kuebix freight migration to production API | Sayer | Not Started | Retry logic for carrier failures
Phase 2 | Hardening | 15-16 | NetSuite integration migration | Sayer | Not Started | OAuth token auto-refresh
Phase 2 | Hardening | 15-16 | HubSpot rewired to call production API | Sayer | Not Started | Thin trigger layer
Phase 2 | Hardening | 15-16 | Load testing at production volume | Sayer | Not Started | 65+ quotes/week
Phase 2 | Finalization | 17-18 | Final regression testing | Sayer | Not Started | Full E2E validation
Phase 2 | Finalization | 17-18 | Documentation update | Sayer | Not Started | Architecture and admin guide
Phase 2 | Finalization | 18 | Phase 2 close-out | Sayer + Leadership | Not Started | Project complete

## Workstream Summary
Phase | Workstream | Weeks | Description
Phase 1 | CPQ Architecture & Configuration | 1-4 | Commerce Hub setup, custom properties, approval workflows, payment terms
Phase 1 | Product Catalog Sync | 1-4 | 700 SKUs extracted from NetSuite via SuiteQL, loaded into HubSpot with custom properties
Phase 1 | NetSuite Quote-to-Order Integration | 1-4, 7-8 | OAuth 2.0 M2M authentication, quote-to-estimate-to-sales-order automation, credit hold checks
Phase 1 | Kuebix Freight Integration | 5-6 | Multi-carrier LTL rate shopping via API, origin warehouse routing, manual override
Phase 1 | Dynamic Weight Calculation Engine | 5-8 | Replaces 5 Excel spreadsheets with modular engine (Dorm, Camp, Dura-Last, SoFlux, Vinyl)
Phase 1 | Quote Template Design | 5-8 | Branded PDF matching NetSuite format -- line items, discounts, tax, freight, terms
Phase 1 | Discount, Tax & Payment Terms | 7-8 | 10% volume discount, state-based tax, prepay/net 10/30/60, credit hold integration
Phase 1 | Training & Documentation | 9-10 | Sales team + admin training sessions (recorded), admin guide, user reference card
Phase 1 | Testing & QA | 9-12 | E2E integration testing, weight validation vs Excel, freight validation, UAT, 2-week hypercare
Phase 1 | Project Management | 1-12 | Kickoff, weekly syncs, milestone reviews, scope management
Phase 2 | Production API Setup (Railway) | 13-14 | Cloud hosting, CI/CD pipeline, monitoring, logging, health checks
Phase 2 | Weight Engine Migration | 13-14 | All 5 product modules + shared utilities migrated with full test coverage
Phase 2 | Kuebix Freight Migration | 15-16 | Freight orchestration moved to production API with retry logic
Phase 2 | NetSuite Integration Migration | 15-16 | OAuth token management, catalog sync, quote-to-order with proper error handling
Phase 2 | HubSpot Rewiring | 15-16 | Custom code actions updated to call production API instead of running logic locally
Phase 2 | Integration Testing | 13-18 | E2E testing, load testing at 65+ quotes/week, regression against Phase 1 baseline
Phase 2 | Project Management | 13-18 | Milestone reviews, documentation updates

## Milestones
Week | Milestone | Attendees | Decision Point
1 | Project Kickoff | Sayer + Full AB Team | Confirm scope, timeline, and access requirements
4 | Foundation Milestone Review | Sayer + Mike, Patrick | Product catalog and NetSuite integration validated
8 | Integration Milestone Review | Sayer + Leadership | Weight engine, freight, and quote-to-order tested
9-10 | UAT Sessions | Sayer + Caleb, Don | Sales team validates quoting workflow
11-12 | Phase 1 Go-Live | Sayer + Full AB Team | Reps begin quoting in HubSpot
12 | Phase 1 Close-Out | Sayer + Mike, Patrick | Go/no-go decision for Phase 2
14 | Phase 2 Midpoint Check | Sayer + Mike, Patrick | Weight engine and API migration validated
18 | Phase 2 Close-Out / Project Complete | Sayer + Leadership | Production platform live, documentation delivered