## Sheet1
Task | Hours
Review SFDC Instance / Sandbox Setup | 4
Data Import into Sandbox for testing | 1
Run SFDC Optimizer / field analysis | 2
Build Sales Flow Stage Artifact & Adjustments | 6
Scope and build project plan | 4
Build Presentation Deck | 3
Review Current Opp Flow documentation and Validation Rules | 4
Begin build of sales path in sandbox | 4
Complete Build Sales Path in Sandbox | 6
Build new record type and stage names | 3
Add New fields and permissions to page layout | 2
Build validations and flows for entry exit criteria | 8
Adjust action buttons | 2
Adjust required fields | 1
Build test cases | 0.5
Run through test cases | 2
review feedback and adjustments | 0.5
make adjustments and retest | 4
Training Session - First Walkthrough | 0.5
Training Video & Walkthrough Doc | 1
Training - Feedback Document & Live review / Upload to Notion | 1
Connect revops sandbox to wagmo production and test change set | 2
Disconnect legacy sandbox from production | 0.5
Push Change Set - Opp Record Type & New Sales Path | 2
Push Change Set - New Fields and stage name / picklist values | 3
Push Change Set - Validations and Flows | 3
Push Change Set - User Permissions / Action Buttons / Page Layouts | 2
Test in production and resolve change set errors | 2
Update Sales Path Verbiage | 1.5
Sales Performance - Reports and Dashboard - Scope and design | 4
1st draft - Report Build | 5
1st draft - dashboard build | 4
Test filtering and data criteria | 1
Apply feedback from 8/27 meeting | 3
Report build - competitor details | 0.5
Setup - Hisotrical Opportunity Trends & check against actuals | 2.5
Partner/Referral build & design | 5
partner referral changes in sandbox | 4.5
Opp type flow changes - in sandbox | 1.5