## Option A vs Option B
STRIVE Global -- V2 Scope Comparison: Option A vs Option B
Workstream | Option A Median Hrs | Option A Median Cost | Option B Median Hrs | Option B Median Cost | Difference
SHARED WORKSTREAMS (in both options)
CRM Architecture & Config Review | 12 | 1800 | 12 | 1800 | --
Pipeline Restructuring | 24 | 3600 | 24 | 3600 | --
Contact & Company Classification + Cleanup | 24 | 3600 | 24 | 3600 | --
Deal Health Scoring & Forecasting | 10 | 1500 | 10 | 1500 | --
Reporting & Dashboards | 20 | 3000 | 20 | 3000 | --
Automations & Workflows | 14 | 2100 | 14 | 2100 | --
Email & Communication Fix | 6 | 900 | 6 | 900 | --
Training: Admin | 6 | 900 | 6 | 900 | --
Training: End Users | 8 | 1200 | 8 | 1200 | --
Training: Executive | 3 | 450 | 3 | 450 | --
UAT, Go-Live & Documentation | 10 | 1500 | 10 | 1500 | --
Project Management (Phase 1) | 18 | 2700 | 18 | 2700 | --
OPTION B ONLY (Phase 2 additions)
CPQ Implementation | -- | -- | 45 | 6750 | +45 hrs
Contract Management Workflows | -- | -- | 11 | 1650 | +11 hrs
Data Enrichment at Scale | -- | -- | 12 | 1800 | +12 hrs
Data Normalization & Dedup (Extended) | -- | -- | 14 | 2100 | +14 hrs
Parent-Child Structure (Broker Packs) | -- | -- | 8 | 1200 | +8 hrs
Email Sequencing | -- | -- | 8 | 1200 | +8 hrs
Marketing Automation Foundation | -- | -- | 11 | 1650 | +11 hrs
Commission Visibility & Validation | -- | -- | 6 | 900 | +6 hrs
NetSuite Integration Prep | -- | -- | 11 | 1650 | +11 hrs
Bill.com Integration Prep | -- | -- | 6 | 900 | +6 hrs
Seat/License Optimization | -- | -- | 3 | 450 | +3 hrs
Advanced Reporting | -- | -- | 11 | 1650 | +11 hrs
Additional Project Management (Phase 2) | -- | -- | 16 | 2400 | +16 hrs
TOTALS | 155 | 23250 | 313 | 46950 | +158 hrs
SUMMARY COMPARISON
| Option A: CRM Foundation | Option B: Full Overhaul
Median Hours | 155 | 313
Median Cost (@$150/hr) | $23,250 | $46,950
Timeline | 8-10 weeks | 16-18 weeks (phased)
Payback Period | 5-7 months | 4-7 months
Includes CPQ | No | Yes (45 hrs)
Includes Marketing | No | Yes (11 hrs)
Includes Integration Prep | No | Yes (NetSuite + Bill.com)
Includes Commission Tracking | No | Yes (visibility + validation)
Can Stand Alone | Yes | Yes (Phase 1 = Option A)
Phase 2 Deferrable | N/A | Yes -- Phase 1 delivers value independently
Green rows = Option B only (not included in Option A)

## Approach Comparison
STRIVE Global -- Full CRM Overhaul V2: Approach Comparison
Dimension | Approach A: Phased (Recommended) | Approach B: Concurrent
Description | Phase 1: CRM Foundation (weeks 1-8) -- pipeline, contacts, dashboards, automations. Phase 2: CPQ, enrichment, integrations, marketing (weeks 9-18). Each phase delivers standalone value. | All workstreams in parallel across 12-14 weeks. Maximum resource intensity.
Total Hours (Median) | 313 hrs across two phases | 313 hrs compressed
Timeline | 16-18 weeks (Phase 1: 8-10 wks + Phase 2: 8-10 wks) | 12-14 weeks
Risk Level | LOW -- Phase 1 de-risks Phase 2; clean data enables CPQ accuracy | HIGH -- dirty data undermines CPQ and reporting; multiple moving parts
Adoption Impact | Team absorbs changes gradually; builds confidence before CPQ launch | All-at-once change; higher cognitive load
Change Management | Two training cycles; Phase 1 habits established before Phase 2 | Single push covering all features
Dependency Risk | LOW -- Phase 2 depends on Phase 1, but Phase 1 is self-contained | HIGH -- CPQ depends on clean pipeline AND contact data simultaneously
Client Resource Demand | Spread over 18 weeks; manageable alongside day-to-day | Concentrated in 14 weeks; significant time commitment
Board Reporting Value | Phase 1 dashboards by week 8; full CPQ and advanced reporting by week 18 | Full suite by week 14 if everything goes to plan
Cost | $46,950 (median at $150/hr) | $46,950 (median at $150/hr)
Budget Flexibility | Can pause after Phase 1 ($23,250) if budget constrained | Full commitment required upfront
Recommendation
Approach A: Phased is strongly recommended. STRIVE's data quality issues make concurrent approach risky -- CPQ built on dirty data produces inaccurate quotes. Phase 1 delivers immediate operational value and can stand alone if Phase 2 is deferred. Estimates calibrated against prior comparable Salesforce engagement and HubSpot industry benchmarks (CPQ: 40-60 hrs industry standard).

## Scoping Estimate
Hourly Rate: | 150
Workstream | Description | Min Hours | Max Hours | Median Hours | Rate | Min Cost | Max Cost | Median Cost | Notes / Assumptions | Actual Hours | Actual Cost | Variance
PHASE 1: CRM FOUNDATION (Weeks 1-8)
CRM Architecture & Config Review | Portal audit, user roles, permissions, team structure, 3-hub assessment, seat review. | 8 | 16 | 12 | 150 | 1200 | 2400 | 1800
Pipeline Restructuring | Pre-pipeline separation, partner/client categories, stage probabilities, required fields, Contracting stage, auto-transitions, deal age reset. | 16 | 32 | 24 | 150 | 2400 | 4800 | 3600
Contact & Company Classification + Cleanup | Contact taxonomy, AI enrichment pilot + full run, normalization, dedup, association fixes, duplicate protection. | 16 | 32 | 24 | 150 | 2400 | 4800 | 3600 | 10 yrs uncoded data. Industry: $5K-$15K for cleanup. Conservative with AI.
Deal Health Scoring & Forecasting | Deal score formula, healthy/at-risk/stale, standardized close reasons, forecasting views. | 6 | 14 | 10 | 150 | 900 | 2100 | 1500 | Scoring defined collaboratively.
Data Normalization & Dedup (Extended) | Full normalization, advanced dedup, merge strategy, ongoing protection. | 10 | 18 | 14 | 150 | 1500 | 2700 | 2100 | Extends Phase 1 cleanup comprehensively.
Parent-Child Structure (Broker Packs) | Association labels, per-broker forms, auto child contact creation, list generation. | 6 | 10 | 8 | 150 | 900 | 1500 | 1200 | Enables microsite-to-app expansion. Depends on form link from Andrea.
Automations & Workflows | Outlook fix, lead source, form-to-CRM, stage notifications, dup protection, pre-pipeline transitions. | 10 | 18 | 14 | 150 | 1500 | 2700 | 2100 | Up to 10 workflows.
Reporting & Dashboards | Partner, seller, CEO/board, pipeline health dashboards. 15 custom reports. Scheduled exports. | 14 | 26 | 20 | 150 | 2100 | 3900 | 3000
Email & Communication Fix | Outlook audit/fix, association rules, domain exclusions. | 4 | 8 | 6 | 150 | 600 | 1200 | 900 | Root cause week 1.
Training: Admin | Andrea + admin. Pipeline, reporting, workflows, data hygiene. | 4 | 8 | 6 | 150 | 600 | 1200 | 900 | 1-2 sessions recorded.
Training: End Users | Sales team. CRM usage, deals, activity, dashboards, mobile. | 6 | 10 | 8 | 150 | 900 | 1500 | 1200 | 2-3 sessions.
Training: Executive | Jodi. Board dashboard, forecasting, scheduling. | 2 | 4 | 3 | 150 | 300 | 600 | 450 | 1 session.
UAT, Go-Live & Documentation (Phase 1) | Test scripts, 2 UAT sessions, bug fixes, admin + user guide, 2-week hypercare. | 8 | 12 | 10 | 150 | 1200 | 1800 | 1500
Project Management (Phase 1) | Kickoff, weekly syncs, status updates, scope control. | 14 | 22 | 18 | 150 | 2100 | 3300 | 2700
Phase 1 Subtotal |  | 124 | 230 | 177 | 150 | 18600 | 34500 | 26550 |  | 0 | 0
PHASE 2: CPQ, ENRICHMENT & INTEGRATIONS (Weeks 9-18)
CPQ Implementation | Product library (apps, microsites, AI, packs, Divi, bundles). Quote templates. E-signatures. Reminders. Multiple pricing models (license+rev share, flat, bundles/discounts). | 35 | 55 | 45 | 150 | 5250 | 8250 | 6750 | Industry benchmark: 40-60 hrs for CPQ rollout (Process Pro Consulting). Multiple pricing models add complexity. V1 was 18 hrs -- significantly under-scoped.
Contract Management Workflows | Quote-to-contract automation. Status tracking. Renewal/expiry workflows. Replaces manual DocuSign through COO. | 8 | 14 | 11 | 150 | 1200 | 2100 | 1650 | Contract templates, status properties, auto-advance on signature.
Data Enrichment at Scale | Full database Breeze AI enrichment. Auto-enrichment for inbound. QA and validation. | 8 | 16 | 12 | 150 | 1200 | 2400 | 1800 | Extends Phase 1 pilot to full database. Includes QA cycle.
Email Sequencing | Broker prospecting, microsite-to-app expansion. 4 sequences + enrollment + reporting. | 6 | 10 | 8 | 150 | 900 | 1500 | 1200 | HubSpot Enterprise sequences included in license.
Marketing Automation Foundation | Newsletter template, 2-3 segmented campaigns, compliance. | 8 | 14 | 11 | 150 | 1200 | 2100 | 1650 | Leverages Marketing Hub (already licensed).
Commission Visibility & Validation | CRM-based commission view, validation workflow for Jodi. | 4 | 8 | 6 | 150 | 600 | 1200 | 900 | Visibility only -- not full calculation engine.
NetSuite Integration Prep | Data readiness, field mapping, gap analysis. PREP ONLY. | 8 | 14 | 11 | 150 | 1200 | 2100 | 1650 | Does NOT include API build. Separate SOW required.
Bill.com Integration Prep | AR/AP field mapping, data readiness. PREP ONLY. | 4 | 8 | 6 | 150 | 600 | 1200 | 900 | Does NOT include build. Separate SOW.
Seat/License Optimization | Audit 23 seats, identify waste, cost savings memo. | 2 | 4 | 3 | 150 | 300 | 600 | 450 | Deliverable: cost savings recommendation.
Advanced Reporting | Automated board reports, pipeline coverage, pace-to-goal, marketing ROI. | 8 | 14 | 11 | 150 | 1200 | 2100 | 1650 | Extends Phase 1 dashboards with Phase 2 data.
Additional Project Management | Phase 2 PM, weekly syncs, milestone reviews. | 12 | 20 | 16 | 150 | 1800 | 3000 | 2400 | ~12% of Phase 2 hours.
Phase 2 Subtotal |  | 103 | 177 | 140 | 150 | 15450 | 26550 | 21000 |  | 0 | 0
OPTIONAL ADD-ON
Client Success Pipeline (Optional) | Client health tracking, health score properties, renewal tracking. Requires CS team discovery. | 8 | 14 | 11 | 150 | 1200 | 2100 | 1650 | Not in project total. Requires separate CS discovery.
PROJECT TOTAL (Phase 1 + Phase 2) |  | 227 | 407 | 317 | 150 | 34050 | 61050 | 47550

## Risk Register
# | Risk | Severity | Likelihood | Impact | Mitigation | Owner | Status
1 | 10 years uncoded contact data -- enrichment may exceed estimates | HIGH | HIGH | Cleanup 2-3x estimate; CPQ associations unreliable | Pilot 500 records in Phase 1. Budget 30% buffer. | Consultant + Andrea | Open
2 | Pipeline under-reporting -- reps on LinkedIn | HIGH | HIGH | Forecast unreliable; CPQ adoption depends on deal entry | Jodi mandates CRM usage. Board briefed on pipeline increase. | Jodi | Open
3 | Scope creep from close relationship | HIGH | MEDIUM | Informal requests; budget overrun on 18-week engagement | Formal SOW. Weekly hours tracking. Change request process. | Consultant + Jodi | Open
4 | Board ROI expectations | HIGH | MEDIUM | Unrealistic timeline expectations | Conservative ranges. 90-day check-in after Phase 1. | Consultant + Jodi | Open
5 | CPQ product library complexity | MEDIUM | HIGH | HubSpot CPQ may not handle all pricing models natively | Audit 5 recent quotes before build. Confirm Enterprise CPQ handles rev share. | Consultant | Open
6 | Seat/license confusion | MEDIUM | HIGH | Paying for unused seats; CPQ may need specific seats | License audit week 1. Cost savings memo. | Consultant + Jodi | Open
7 | NetSuite/Bill.com scope bleed | MEDIUM | MEDIUM | Prep becomes build without budget | Explicit boundary: prep only. Build = separate SOW. | Consultant | Open
8 | Adoption risk | MEDIUM | HIGH | CRM + CPQ unused; ROI unrealized | Executive mandate. Rep dashboards. Sequences reduce manual work. | Jodi + Andrea | Open
9 | Outlook email logging defect | LOW | MEDIUM | HubSpot support escalation timeline | Diagnose week 1. Open ticket if needed. | Consultant | Open
10 | COO ambiguity | LOW | LOW | Admin access issues | Clarify at kickoff. | Consultant | Open

## Assumptions & Exclusions
Scope Assumptions
1 | HubSpot Sales Hub Enterprise (existing instance -- reconfiguration)
2 | Up to 23 licensed users across core, sales, and service seats
3 | Outlook as primary email platform
4 | Up to 40 custom properties (expanded for CPQ and enrichment)
5 | 1 active sales pipeline with pre-pipeline separated
6 | 2 deal categories: partner-level and client-level
7 | Stage probability mapping using Jodi's framework
8 | AI enrichment using HubSpot Breeze credits (5-10K)
9 | Up to 12 automated workflows
10 | 4-5 dashboards with up to 20 custom reports
11 | Complete product/pricing inventory provided before CPQ build
12 | CPQ hours based on industry benchmark of 40-60 hrs (Process Pro Consulting)
13 | Marketing Hub leveraged for campaigns (already licensed)
14 | 16-18 week phased timeline
15 | Phase 1 can stand alone if Phase 2 deferred
16 | Estimates calibrated against prior Salesforce engagement and industry benchmarks
17 | All work conducted remotely
18 | Scope changes via formal change request
Out of Scope
1 | NetSuite integration build (prep only)
2 | Bill.com integration build (prep only)
3 | Client Success pipeline (optional add-on)
4 | Full commission calculation engine
5 | Custom API development beyond HubSpot native
6 | Other CRMs
7 | External data migration
8 | Managed services beyond hypercare per phase
9 | License procurement
10 | AI knowledge assistant
11 | LinkedIn Navigator integration
Client Responsibilities
1 | Designate primary POC (Andrea)
2 | Jodi + Andrea availability for sessions
3 | Complete product/pricing inventory before Phase 2 CPQ
4 | Contact classification rules and enrichment validation
5 | Deal stage definitions and probability framework
6 | Close won/lost reason categories
7 | Mandate CRM usage (Jodi exec sponsorship)
8 | Share 3-5 recent quotes across deal types
9 | UAT testing per phase
10 | HubSpot admin access
11 | NetSuite admin contact for integration prep
12 | Commission validation requirements
Open Items
1 | Contact/company/deal record counts (pending access)
2 | Product/pricing inventory for CPQ
3 | Service Hub usage
4 | COO identity and admin access
5 | Outlook defect root cause
6 | Existing workflow inventory
7 | Historical deal data reliability
8 | Microsite form link
9 | NetSuite entity structure
10 | SOW signing authority
11 | Divi positioning

## CRM Foundations Configuration -
STRIVE Global -- CRM Foundation V2: Approach Comparison
Dimension | Approach A: Foundation First (Recommended) | Approach B: Quick Wins First
Description | Data cleanup and contact classification first (weeks 1-5), then pipeline restructuring and dashboards (weeks 6-10). Build on clean foundation. | Pipeline restructuring and dashboards first (weeks 1-5), then data cleanup and enrichment (weeks 6-10). Deliver visible wins early.
Total Hours (Median) | 155 hrs | 155 hrs
Timeline | 8-10 weeks | 8-10 weeks
Risk Level | LOW -- clean data enables accurate dashboards from day one | MEDIUM -- dashboards built on dirty data show misleading metrics initially
Adoption Impact | Slower initial visibility but higher trust in data when dashboards launch | Faster dashboard delivery but reps may distrust inaccurate early reports
Change Management | Gradual -- team sees data improving before process changes | Immediate -- team gets new pipeline and dashboards right away
Dependency Risk | LOW -- data cleanup is independent of other workstreams | MEDIUM -- dashboards depend on data quality for accuracy
Client Resource Demand | Higher upfront (contact exports, classification rules, validation) | Lower upfront but higher mid-project for data cleanup
Board Reporting Value | Clean, trustworthy reports available by week 8 | Reports available by week 5 but accuracy improves through week 10
Cost | $23,250 (median at $150/hr) | $23,250 (median at $150/hr)
Recommendation
Approach A: Foundation First is recommended. STRIVE has 10 years of uncoded contact data and unreliable pipeline metrics. Building dashboards on dirty data risks eroding trust in the CRM. Clean the data first, then deliver dashboards the team and board can trust from day one. This also aligns with Jodi's emphasis on building a strong data infrastructure as the foundation for future AI capabilities.

## Scoping Estimate (1)
Hourly Rate: | 150
Workstream | Description | Min Hours | Max Hours | Median Hours | Rate | Min Cost | Max Cost | Median Cost | Notes / Assumptions | Actual Hours | Actual Cost | Variance
CRM Architecture & Config Review | Portal audit, user roles/permissions, team structure reconfig. Seat/license review across 3 hubs (sales, marketing, service). Enterprise instance complexity assessment. | 8 | 16 | 12 | 150 | 1200 | 2400 | 1800 | Wagmo comparable: 14 hrs discovery. HubSpot simpler than SFDC but 3-hub Enterprise with 23 seats adds complexity.
Pipeline Restructuring | Separate pre-pipeline from active pipeline. Partner-level vs. client-level deal categories. Stage probability mapping (5/20/40/50/60/80/90/100). Required fields per stage. Add Contracting stage. Auto-transition workflows with deal age reset. | 16 | 32 | 24 | 150 | 2400 | 4800 | 3600 | Wagmo benchmark: 36 hrs for simpler Salesforce pipeline. HubSpot offset: -20%. Strive complexity premium: +40% (2 categories, pre-pipeline, probabilities, auto-transitions). Net: ~24 hrs median.
Contact & Company Classification + Cleanup | Contact type taxonomy (client/prospect/broker/partner). AI enrichment pilot (500 records) then full run using HubSpot Breeze credits. Normalization, deduplication, association fixes. Duplicate protection rules. | 16 | 32 | 24 | 150 | 2400 | 4800 | 3600 | 10 years uncoded data. Industry benchmark: $5K-$15K for cleanup = 33-100 hrs at $150. Conservative estimate with AI acceleration. +30-50% data quality premium.
Deal Health Scoring & Forecasting | Deal score: stage + time-in-stage + activity recency. Healthy/at-risk/stale classification. Standardized close won/lost reasons (categorized dropdowns replacing free-form). Forecasting views. | 6 | 14 | 10 | 150 | 900 | 2100 | 1500 | Scoring formula and thresholds defined collaboratively. Close reason categories defined before implementation.
Reporting & Dashboards | Partner dashboard (clonable, quick filters). Seller KPI dashboard. CEO/board dashboard (bookings, pipeline coverage, win rate, deal age). Pipeline health dashboard. Up to 15 custom reports. | 14 | 26 | 20 | 150 | 2100 | 3900 | 3000 | Wagmo benchmark: 20 hrs for 2 dashboards + 6 reports. Strive needs 4 dashboards + 15 reports. AI accelerates report logic but iteration cycles take time.
Automations & Workflows | Fix Outlook email logging issue. Lead source tracking automation. Form-to-CRM for microsite client capture. Deal stage-change notifications. Duplicate protection rules. Pre-pipeline auto-transition. | 10 | 18 | 14 | 150 | 1500 | 2700 | 2100 | Up to 10 automated workflows (increased from 8). Outlook fix may require HubSpot support ticket. Includes pre-pipeline transition automation.
Email & Communication Fix | Outlook integration audit and fix. Email association rules to prevent logging to all related deals. Domain exclusions for internal communications. | 4 | 8 | 6 | 150 | 600 | 1200 | 900 | Root cause diagnosis week 1. If config fix: 2-4 hrs. If platform bug: HubSpot support escalation.
Training: Admin | Andrea + designated admin. Pipeline management, reporting, workflow admin, data hygiene, enrichment tools. | 4 | 8 | 6 | 150 | 600 | 1200 | 900 | Wagmo training was minimal (2.5 hrs total). Strive needs proper formal sessions. 1-2 sessions with recording.
Training: End Users | Sales team. Daily CRM usage, deal entry, activity logging, dashboard consumption, mobile app. | 6 | 10 | 8 | 150 | 900 | 1500 | 1200 | 2-3 sessions. Emphasis on showing reps how CRM data benefits them.
Training: Executive | Jodi. Board dashboard walkthrough, forecast consumption, report scheduling, export for board decks. | 2 | 4 | 3 | 150 | 300 | 600 | 450 | 1 session focused on board reporting.
UAT, Go-Live & Documentation | Test scripts, 2 UAT sessions with key stakeholders, bug fix window, go-live cutover plan. Admin guide + user guide. 2-week hypercare. | 8 | 12 | 10 | 150 | 1200 | 1800 | 1500 | Wagmo testing: 7 hrs. Add documentation deliverables and hypercare setup. Formal test scripts not done at Wagmo.
Project Management | Kickoff, weekly syncs, status updates, change management, milestone reviews. Scope creep prevention. | 14 | 22 | 18 | 150 | 2100 | 3300 | 2700 | ~12% of total. Wagmo lesson: zero formal PM led to scope creep. This prevents that.
TOTAL |  | 108 | 202 | 155 | 150 | 16200 | 30300 | 23250 |  | 0 | 0

## Risk Register (1)
# | Risk | Severity | Likelihood | Impact | Mitigation | Owner | Status
1 | 10 years of uncoded contact data -- AI enrichment scope may exceed estimates | HIGH | HIGH | Data cleanup takes 2-3x estimate; marketing segmentation delayed; project timeline extends | Run AI enrichment pilot on 500 records first. Measure classification accuracy before full run. Budget 30% buffer. | Consultant + Andrea | Open
2 | Pipeline under-reporting -- reps using LinkedIn and manual quoting outside CRM | HIGH | HIGH | Forecasting unreliable during transition; board sees pipeline dip before improvement | Jodi mandates CRM usage pre-launch. Set data entry expectations. Brief board that reported pipeline will increase as capture improves. | Jodi (executive sponsor) | Open
3 | Scope creep from close business relationship | HIGH | MEDIUM | Informal requests bypass SOW; hours consumed without authorization; budget overrun | SOW signed by budget authority. All change requests documented formally. Weekly hours tracking visible to client. Lesson learned from prior engagement. | Consultant + Jodi | Open
4 | Board ROI expectations overpromise | HIGH | MEDIUM | Board approves but expects unrealistic timeline or savings; sets up failure | ROI narrative uses conservative estimates with ranges. 90-day KPI check-in. | Consultant + Jodi | Open
5 | Seat/license confusion -- mixed versions, unused seats | MEDIUM | HIGH | Paying for unused seats; features expected but unavailable | License audit in week 1. Cost savings memo before configuration work. | Consultant + Jodi | Open
6 | Adoption risk -- reps prefer LinkedIn | MEDIUM | HIGH | New CRM configuration goes unused; ROI unrealized | Executive mandate. Make CRM easier than alternatives. Rep-level dashboards. | Jodi + Andrea | Open
7 | Outlook email logging defect | LOW | MEDIUM | Fix may require HubSpot support escalation with unknown timeline | Diagnose week 1. Open HubSpot ticket if platform bug. | Consultant | Open
8 | COO identity ambiguity (Lauren vs. Zach Beegal) | LOW | LOW | Miscommunication on stakeholder authority | Clarify org chart at kickoff. | Consultant | Open

## Assumptions & Exclusions (1)
Scope Assumptions
1 | HubSpot Sales Hub Enterprise (existing instance -- reconfiguration, not net-new)
2 | Up to 23 licensed users across 3 core, 10 sales, and 10 service seats
3 | Outlook as primary email platform (with known logging defect to be resolved)
4 | Up to 30 custom contact/company properties
5 | 1 active sales pipeline with pre-pipeline separated
6 | 2 deal categories: partner-level and client-level (same stages, different segmentation)
7 | Stage probability mapping using Jodi's framework (5/20/40/50/60/80/90/100)
8 | Contact type classification: client, prospect, broker, partner
9 | AI enrichment using HubSpot Breeze credits (5-10K credits available)
10 | Up to 10 automated workflows
11 | 4 reporting dashboards with up to 15 custom reports
12 | 8-10 week implementation timeline
13 | All work conducted remotely unless otherwise agreed
14 | Estimates calibrated against prior comparable engagement (Wagmo/Salesforce) and industry benchmarks
15 | Any scope changes managed through formal change request and may impact cost or timing
Out of Scope
1 | CPQ / quoting / product library build (see Option B: Full CRM Overhaul)
2 | Email sequencing or sales cadence automation
3 | Marketing automation (newsletters, campaigns, landing pages)
4 | NetSuite, Bill.com, or any ERP/financial system integration
5 | Client Success pipeline or client health scoring
6 | Commission tracking or calculation automation
7 | Contract management or e-signature workflows
8 | Custom API development or middleware (n8n/Zapier)
9 | Data migration from external systems (HubSpot internal cleanup only)
10 | Ongoing managed services beyond 2-week hypercare
11 | HubSpot license procurement or tier changes
Client Responsibilities
1 | Designate primary point of contact (Andrea recommended)
2 | Ensure Jodi and Andrea availability for discovery, UAT, and training sessions
3 | Provide contact classification rules and validate AI enrichment results
4 | Confirm deal stage definitions and probability framework before pipeline build
5 | Communicate standardized close won/lost reason categories
6 | Mandate CRM usage across sales team (executive sponsorship from Jodi)
7 | Complete UAT testing within agreed timeline
8 | Provide access to HubSpot admin portal
9 | Share 3-5 recent quotes/proposals for reference
Open Items
1 | Exact contact/company/deal record counts (pending portal access)
2 | Service Hub usage details -- preserve or deprecate?
3 | COO identity and HubSpot admin access ownership
4 | Outlook email logging defect root cause
5 | Existing workflow inventory
6 | Historical deal data reliability for probability calibration
7 | Microsite client intake form link from Andrea
8 | SOW signing authority (CEO or board)