## Approach Comparison
STRIVE Global -- Full CRM Overhaul: Approach Comparison
Dimension | Approach A: Phased (Recommended) | Approach B: Concurrent
Description | Phase 1: CRM Foundation (weeks 1-6) -- pipeline, contacts, dashboards, automations. Phase 2: CPQ, enrichment, integrations, marketing (weeks 7-14). Each phase delivers standalone value. | All workstreams executed in parallel across 8-10 weeks. Single cutover. Maximum resource intensity.
Total Hours (Median) | 216 hrs across two phases | 216 hrs compressed
Timeline | 14 weeks (Phase 1: 6 wks + Phase 2: 8 wks) | 8-10 weeks
Risk Level | LOW -- Phase 1 de-risks Phase 2; clean data enables CPQ accuracy | HIGH -- dirty data undermines CPQ and reporting from day one; multiple moving parts
Adoption Impact | Team absorbs changes gradually; builds confidence before CPQ launch | All-at-once change; higher cognitive load; risk of feature overwhelm
Change Management | Two training cycles; Phase 1 habits established before Phase 2 adds complexity | Single training push covering all features; harder to absorb
Dependency Risk | LOW -- Phase 2 depends on Phase 1, but Phase 1 is self-contained | HIGH -- CPQ depends on product library AND clean pipeline AND contact data simultaneously
Client Resource Demand | Spread over 14 weeks; manageable alongside day-to-day operations | Concentrated in 8-10 weeks; significant time commitment from Andrea and Jodi
Board Reporting Value | Phase 1 delivers board dashboards by week 6; Phase 2 adds CPQ and advanced reporting by week 14 | Full reporting suite available by week 10 if everything goes to plan
Cost | $32,400 (median at $150/hr) | $32,400 (median at $150/hr)
Budget Flexibility | Can pause after Phase 1 ($17,850) if budget constrained; Phase 2 becomes a separate engagement | Full commitment required upfront; no natural pause point
Recommendation
Approach A: Phased is strongly recommended. STRIVE's data quality issues make a concurrent approach risky -- CPQ built on dirty contact and company data will produce inaccurate quotes and unreliable pipeline reporting. The phased approach also aligns with Jodi's stated goal of being "cost-effective this year while building foundation for future scaling." Phase 1 delivers immediate operational value (pipeline clarity, board dashboards, clean data), and Phase 2 builds on that foundation with CPQ, enrichment, and integration prep. If budget is constrained, Phase 1 can stand alone as a complete engagement.

## Scoping Estimate
Hourly Rate: | 150
Workstream | Description | Min Hours | Max Hours | Median Hours | Rate | Min Cost | Max Cost | Median Cost | Notes / Assumptions | Actual Hours | Actual Cost | Variance
PHASE 1: CRM FOUNDATION (Weeks 1-6)
CRM Architecture & Config Review | Portal audit, user roles/permissions, team structure reconfiguration for existing Enterprise instance | 6 | 12 | [5 empty] | Assumes existing HubSpot Sales Hub Enterprise. Up to 23 seat users.
Pipeline Restructuring | Separate pre-pipeline from active pipeline. Partner-level vs. client-level deal categories. Stage probability mapping. Required fields per stage. Add Contracting stage. | 10 | 18 | [5 empty] | Two deal categories in same pipeline. Jodi's probability framework as starting point.
Contact & Company Classification + Cleanup | Contact type taxonomy (client/prospect/broker/partner). AI enrichment using HubSpot Breeze credits. Normalization, deduplication, association fixes. | 14 | 24 | [5 empty] | 10 years of uncoded data. +30-50% data quality premium. Pilot enrichment on 500 records first.
Deal Health Scoring & Forecasting | Deal score: stage + time-in-stage + activity recency. Healthy/at-risk/stale classification. Standardized close won/lost reasons. | 6 | 12 | [5 empty] | Scoring formula defined collaboratively with Andrea and Jodi.
Reporting & Dashboards | Partner dashboard (clonable, quick filters). Seller KPI dashboard. CEO/board dashboard. Up to 12 custom reports. | 10 | 18 | [5 empty] | Covers all metrics Andrea identified: open deals, pipeline value, avg deals/week, etc.
Automations & Workflows | Fix Outlook email logging. Lead source tracking. Form-to-CRM for microsite capture. Stage-change notifications. Duplicate protection. | 8 | 16 | [5 empty] | Up to 8 automated workflows.
Email & Communication Fix | Outlook integration audit/fix. Email association rules. Domain exclusions. | 4 | 8 | [5 empty] | Root cause diagnosis week 1.
Training: Admin | Andrea + admin. Pipeline management, reporting, workflow admin, data hygiene. | 4 | 8 | [5 empty] | 1-2 sessions with recording.
Training: End Users | Sales team. Daily CRM usage, deal entry, activity logging, dashboards. | 6 | 10 | [5 empty] | 2-3 sessions.
Training: Executive | Jodi. Board dashboard, forecast consumption, scheduling. | 2 | 4 | [5 empty] | 1 session.
UAT, Go-Live & Documentation (Phase 1) | Test scripts, 2 UAT sessions, bug fixes, admin guide, user guide, 2-week hypercare. | 6 | 10 | [5 empty] | Phase 1 go-live and hypercare.
Project Management (Phase 1) | Kickoff, weekly syncs, status updates. | 10 | 16 | [5 empty] | ~12% of Phase 1 hours.
Phase 1 Subtotal
PHASE 2: CPQ, ENRICHMENT & INTEGRATIONS (Weeks 7-14)
CPQ Implementation | Product library build (apps, microsites, AI assistant, broker packs, Divi, bundles). Quote template design. E-signature config. Automated quote reminders. Multiple pricing models. | 12 | 24 | [5 empty] | Requires complete product/pricing inventory from Andrea. License+rev share, flat per-head, bundles/discounts.
Contract Management Workflows | Quote-to-contract automation. Contract status tracking. Renewal and expiry workflows. | 6 | 12 | [5 empty] | Replaces manual DocuSign process through COO.
Data Enrichment at Scale | HubSpot Breeze AI credits (5-10K). Enrichment rules for auto-classification on inbound. QA and validation of results. | 6 | 12 | [5 empty] | Extends Phase 1 pilot enrichment to full database.
Data Normalization & Dedup (Extended) | Full database normalization. Advanced deduplication rules. Merge strategy. Ongoing duplicate protection. | 8 | 16 | [5 empty] | Extends Phase 1 basic cleanup to comprehensive database overhaul.
Parent-Child Structure (Broker Packs) | Association labels. Per-broker intake forms. Automated child contact creation from form submissions. List generation by parent broker. | 4 | 8 | [5 empty] | Enables microsite-to-app expansion prospecting. Depends on form link from Andrea.
Email Sequencing | Broker prospecting sequences. Microsite-to-app expansion outreach. Up to 4 sequences. | 4 | 8 | [5 empty] | Using HubSpot Sales Hub Enterprise sequences (included in current license).
Marketing Automation Foundation | Newsletter template. 2-3 segmented campaigns by contact type (client, broker, prospect). Unsubscribe and compliance setup. | 6 | 12 | [5 empty] | Leverages Marketing Hub (already licensed). CAN-SPAM compliance.
Commission Visibility & Validation | CRM-based commission view tied to closed-won deals. Validation workflow for Jodi before release. Replaces manual spreadsheet reconciliation. | 4 | 8 | [5 empty] | View and validation only -- not full commission calculation engine.
NetSuite Integration Prep | Data cleanup to enable future API connection. Field mapping documentation. Data readiness assessment. | 6 | 12 | [5 empty] | PREP ONLY. Actual integration build requires separate SOW with NetSuite admin involvement.
Bill.com Integration Prep | AR/AP field mapping. Data readiness assessment for future integration. | 4 | 8 | [5 empty] | PREP ONLY. Actual integration build requires separate SOW.
Seat/License Optimization | Audit 23 current seats (3 core, 10 sales, 10 service). Identify unused or misallocated seats. Cost savings memo. | 2 | 4 | [5 empty] | Deliverable: cost savings recommendation with specific seat changes.
Advanced Reporting | Automated board reports (scheduled delivery). Pipeline coverage vs. quota. Pace-to-goal tracking. Marketing ROI reporting. | 6 | 12 | [5 empty] | Extends Phase 1 dashboards with CPQ and marketing data.
Additional Project Management | Phase 2 PM: weekly syncs, milestone reviews, change management. | 8 | 14 | [5 empty] | ~12% of Phase 2 hours.
Phase 2 Subtotal
OPTIONAL ADD-ON
Client Success Pipeline (Optional) | Client health tracking (replace Excel). Health score properties. Renewal tracking. Requires separate discovery with CS team. | 6 | 10 | [5 empty] | Requires separate discovery call with Client Success team. Not included in project total.
PROJECT TOTAL (Phase 1 + Phase 2)

## Risk Register
# | Risk | Severity | Likelihood | Impact | Mitigation | Owner | Status
1 | 10 years of uncoded contact data -- AI enrichment scope may exceed estimates | HIGH | HIGH | Data cleanup takes 2-3x estimate; CPQ product associations unreliable; marketing segmentation delayed | Run AI enrichment pilot on 500 records in Phase 1. Measure accuracy before Phase 2 full run. Budget 30% buffer. | Consultant + Andrea | Open
2 | Pipeline under-reporting -- reps using LinkedIn and manual quoting outside CRM | HIGH | HIGH | Forecasting unreliable during transition; board sees pipeline dip before improvement; CPQ adoption depends on reps entering deals | Jodi mandates CRM usage pre-launch. Set expectations. Brief board that pipeline will increase as capture improves. | Jodi (executive sponsor) | Open
3 | Scope creep from close business relationship | HIGH | MEDIUM | Informal requests bypass SOW; hours consumed without authorization; budget overrun on 14-week engagement | SOW signed by budget authority. All changes documented. Weekly hours tracking visible to client. | Consultant + Jodi | Open
4 | Board ROI expectations overpromise | HIGH | MEDIUM | Board approves but expects unrealistic timeline or savings; Phase 2 pressure to deliver faster | Conservative ROI estimates with ranges. 90-day KPI check-in after Phase 1. Phase 2 ROI measured separately. | Consultant + Jodi | Open
5 | CPQ product library complexity -- multiple pricing models (license+rev share, flat, bundles) | MEDIUM | MEDIUM | HubSpot CPQ may not handle all pricing models natively; partial manual process remains; quote accuracy issues | Audit 5 recent quotes across deal types before building product library. Confirm Enterprise CPQ handles rev share structures. Identify edge cases early. | Consultant | Open
6 | Seat/license confusion -- mixed versions, potential unused seats | MEDIUM | HIGH | Paying for unused seats; features expected but unavailable; CPQ features may require specific seat types | Complete license audit in week 1. Produce cost savings memo. Confirm CPQ capabilities on current Enterprise tier. | Consultant + Jodi | Open
7 | NetSuite/Bill.com integration scope bleed -- prep work reveals integration is harder than expected | MEDIUM | MEDIUM | Client pushes for actual integration build without additional budget; prep-only boundary violated | Scope boundary explicitly states "prep only." Integration build requires separate SOW with NetSuite admin involvement. Document boundary in kickoff. | Consultant | Open
8 | Adoption risk -- sales reps prefer LinkedIn Sales Navigator over CRM | MEDIUM | HIGH | New CRM and CPQ configuration goes unused; ROI unrealized; board investment wasted | Executive mandate from Jodi. Make CRM easier than alternatives. Rep-level dashboards. Email sequences reduce manual prospecting effort. | Jodi + Andrea | Open
9 | Outlook email logging defect -- emails logging to all associated deals | LOW | MEDIUM | Fix may require HubSpot support escalation; workaround needed; email sequences may compound the issue | Diagnose root cause in week 1. If platform bug, open HubSpot support ticket. Email sequences designed to avoid multi-deal logging. | Consultant | Open
10 | COO identity ambiguity (Lauren vs. Zach Beegal) | LOW | LOW | Miscommunication on stakeholder authority; admin access issues | Clarify org chart at kickoff. | Consultant | Open

## Assumptions & Exclusions
Scope Assumptions
1 | HubSpot Sales Hub Enterprise (existing instance -- reconfiguration, not net-new)
2 | Up to 23 licensed users across 3 core, 10 sales, and 10 service seats
3 | Outlook as primary email platform
4 | Up to 40 custom contact/company properties (expanded for CPQ and enrichment)
5 | 1 active sales pipeline with pre-pipeline separated
6 | 2 deal categories: partner-level and client-level
7 | Stage probability mapping using Jodi's framework
8 | Contact type classification: client, prospect, broker, partner
9 | AI enrichment using HubSpot Breeze credits (5-10K credits)
10 | Up to 12 automated workflows (expanded for CPQ and marketing)
11 | 4-5 reporting dashboards with up to 20 custom reports
12 | Complete product/pricing inventory provided by Andrea before CPQ build
13 | HubSpot Marketing Hub leveraged for newsletter and campaign automation
14 | 10-14 week implementation timeline (phased)
15 | Phase 1 can stand alone if Phase 2 is deferred
16 | All work conducted remotely unless otherwise agreed
17 | Any scope changes managed through formal change request
Out of Scope
1 | NetSuite integration build (prep only -- actual build requires separate SOW)
2 | Bill.com integration build (prep only -- actual build requires separate SOW)
3 | Client Success pipeline (available as optional add-on; requires CS team discovery)
4 | Full commission calculation engine (visibility and validation only)
5 | Custom API development or middleware beyond HubSpot native integrations
6 | Salesforce or any CRM other than HubSpot
7 | Data migration from external systems (internal HubSpot cleanup only)
8 | Ongoing managed services beyond 2-week hypercare per phase
9 | HubSpot license procurement or tier changes (recommendations provided)
10 | Hardware, IT infrastructure, or network changes
11 | AI knowledge assistant for sales onboarding (future initiative)
12 | LinkedIn Sales Navigator integration (recommended for future)
Client Responsibilities
1 | Designate primary point of contact (Andrea recommended)
2 | Ensure Jodi and Andrea availability for discovery, UAT, and training sessions
3 | Provide complete product/pricing inventory with all SKUs, bundles, and pricing models before Phase 2 CPQ build
4 | Provide contact classification rules and validate AI enrichment results
5 | Confirm deal stage definitions and probability framework
6 | Communicate standardized close won/lost reason categories
7 | Mandate CRM usage across sales team (executive sponsorship from Jodi)
8 | Share 3-5 recent quotes/proposals across deal types for CPQ reference
9 | Complete UAT testing within agreed timeline for each phase
10 | Provide access to HubSpot admin portal
11 | Identify NetSuite admin contact for integration prep coordination
12 | Provide commission validation requirements and current spreadsheet structure
Open Items
1 | Exact contact/company/deal record counts (pending portal access)
2 | Complete product/pricing inventory for CPQ build
3 | Service Hub usage details -- preserve or deprecate?
4 | COO identity and HubSpot admin access ownership
5 | Outlook email logging defect root cause
6 | Existing workflow inventory
7 | Historical deal data reliability for probability calibration
8 | Microsite client intake form link
9 | NetSuite entity structure and admin contact
10 | SOW signing authority (CEO or board)
11 | Divi product positioning (standalone vs. bundled)