## Option A vs Option B
STRIVE Global -- V2 Scope Comparison: Option A vs Option B
Workstream | Option A Median Hrs | Option A Median Cost | Option B Median Hrs | Option B Median Cost | Difference
SHARED WORKSTREAMS (in both options)
CRM Architecture & Config Review | 12 | 1800 | 12 | 1800 | --
Pipeline Restructuring | 24 | 3600 | 24 | 3600 | --
Contact & Company Classification + Cleanup | 24 | 3600 | 24 | 3600 | --
Deal Health Scoring & Forecasting | 10 | 1500 | 10 | 1500 | --
Reporting & Dashboards | 20 | 3000 | 20 | 3000 | --
Automations & Workflows | 14 | 2100 | 14 | 2100 | --
Email & Communication Fix | 6 | 900 | 6 | 900 | --
Training: Admin | 6 | 900 | 6 | 900 | --
Training: End Users | 8 | 1200 | 8 | 1200 | --
Training: Executive | 3 | 450 | 3 | 450 | --
UAT, Go-Live & Documentation | 10 | 1500 | 10 | 1500 | --
Project Management (Phase 1) | 18 | 2700 | 18 | 2700 | --
OPTION B ONLY (Phase 2 additions)
CPQ Implementation | -- | -- | 45 | 6750 | +45 hrs
Contract Management Workflows | -- | -- | 11 | 1650 | +11 hrs
Data Enrichment at Scale | -- | -- | 12 | 1800 | +12 hrs
Data Normalization & Dedup (Extended) | -- | -- | 14 | 2100 | +14 hrs
Parent-Child Structure (Broker Packs) | -- | -- | 8 | 1200 | +8 hrs
Email Sequencing | -- | -- | 8 | 1200 | +8 hrs
Marketing Automation Foundation | -- | -- | 11 | 1650 | +11 hrs
Commission Visibility & Validation | -- | -- | 6 | 900 | +6 hrs
NetSuite Integration Prep | -- | -- | 11 | 1650 | +11 hrs
Bill.com Integration Prep | -- | -- | 6 | 900 | +6 hrs
Seat/License Optimization | -- | -- | 3 | 450 | +3 hrs
Advanced Reporting | -- | -- | 11 | 1650 | +11 hrs
Additional Project Management (Phase 2) | -- | -- | 16 | 2400 | +16 hrs
TOTALS | 155 | 23250 | 313 | 46950 | +158 hrs
SUMMARY COMPARISON
| Option A: CRM Foundation | Option B: Full Overhaul
Median Hours | 155 | 313
Median Cost (@$150/hr) | $23,250 | $46,950
Timeline | 8-10 weeks | 16-18 weeks (phased)
Payback Period | 5-7 months | 4-7 months
Includes CPQ | No | Yes (45 hrs)
Includes Marketing | No | Yes (11 hrs)
Includes Integration Prep | No | Yes (NetSuite + Bill.com)
Includes Commission Tracking | No | Yes (visibility + validation)
Can Stand Alone | Yes | Yes (Phase 1 = Option A)
Phase 2 Deferrable | N/A | Yes -- Phase 1 delivers value independently
Green rows = Option B only (not included in Option A)