## Scoping Estimate
Hourly Rate: | 150
Workstream | Description | Min Hours | Max Hours | Median Hours | Rate | Min Cost | Max Cost | Median Cost | Notes / Assumptions | Actual Hours | Actual Cost | Hour Variance (Actual - Median) | Cost Variance (Actual - Median) | Variance Notes
CRM Architecture & Setup | HubSpot Sales Hub Professional portal configuration, user roles/permissions for 5 paid seats + view-only access, team structure (M&A team, Real Estate team, Operations), branding, default settings | 6 | 10 | 8 |  |  |  |  | Assumes HubSpot Sales Hub Professional; 5 paid seats + view-only for Jess/Brian; FINRA compliance review of tracking settings
Contact & Company Management | Custom contact/company properties (up to 25), lifecycle stages for companies (Unknown > Known Opportunity > Active Deal > Portfolio Company > Sold), association labels, contact categories (deal sourcing, vendors, LPs, lenders), parent-child company taxonomy, dedup strategy | 8 | 14 | 11 |  |  |  |  | Lifecycle stages customized for PE fund; parent-child associations for portfolio companies; assumes up to 25 custom properties
Pipeline & Deal Management: M&A | 5-stage M&A pipeline (Pre-Screen Opportunity > NDA Signed > Marketing Material Review > Offer Submitted/Mgmt Presentations & Diligence > LOI Signed/Closing), deal properties, required fields per stage, review tracking properties (partner review checkboxes) | 6 | 10 | 8 |  |  |  |  | Includes partner review tracking properties; stage definitions confirmed in discovery; closed-won becomes Portfolio Company lifecycle stage
Pipeline & Deal Management: Real Estate | Separate pipeline for parking garage deals with customized stages, deal properties, and tracking fields specific to real estate acquisition lifecycle | 6 | 10 | 8 |  |  |  |  | CONTINGENT: Stages TBD pending discovery call with Vijay and Philip; estimate assumes comparable complexity to M&A pipeline
Automations & Workflows | Deal stage progression triggers, partner review notification workflows, NDA status tracking, deal-to-portfolio-company lifecycle automation, task creation for new deal stages, basic lead routing | 10 | 18 | 14 |  |  |  |  | Requires Sales Hub Professional for workflow automation; up to 8 workflows; NDA attachment automation limited without e-signature tool
Email & Communication Setup | Outlook integration for 5 users (HubSpot Sales Extension/Add-in), email tracking configuration, connected inbox setup, calendar sync, meeting link configuration | 6 | 10 | 8 |  |  |  |  | All users on Outlook/M365; includes HubSpot Outlook add-in installation per user; FINRA review needed on email tracking pixels
Reporting & Dashboards | M&A pipeline dashboard, Real Estate pipeline dashboard, conversion rate reports, deal velocity metrics, basic activity reporting, Breeze AI search configuration for meeting notes | 6 | 12 | 9 |  |  |  |  | Assumes 2-3 dashboards with up to 8 custom reports; Breeze AI note search is best-effort (new feature, limited guarantees)
Data Migration: Contact Import | Create error-free Excel import template aligned to HubSpot properties, support Frank/Pavel in populating template, field mapping, test load, validation, final import, post-import dedup review | 8 | 16 | 12 |  |  |  |  | Client populates template; assumes under 1,000 contacts initially from LinkedIn exports and manual entry; 1 test load before final import
Training: Admin | Power user training for Frank covering portal settings, property management, pipeline management, workflow editing, reporting, user management | 4 | 8 | 6 |  |  |  |  | 1-2 sessions; Frank is primary admin; includes walk-through of all configurable areas
Training: End Users | End-user training for deal team (Pavel, Vijay, Philip) and EA covering daily CRM usage, Outlook integration, deal updates, contact management, mobile app | 4 | 8 | 6 |  |  |  |  | 1-2 sessions; may split M&A and Real Estate teams; includes Outlook add-in setup walkthrough
Training: Operations (Optional) | Light training for Jess on email tools and basic CRM navigation if marketing tools are added later | 2 | 4 | 3 |  |  |  |  | Optional; Cameron offered 30-min walkthrough; only needed if Jess will use email/marketing features
UAT & Go-Live | User acceptance testing across both pipelines, test scripts, bug fixes, go-live cutover plan, 2-week hypercare support | 6 | 12 | 9 |  |  |  |  | Includes test script creation, 2 UAT sessions, bug fix window, go-live checklist, 2 weeks post-launch support
Documentation & SOPs | Process documentation, user guide, admin reference guide, Outlook integration quick-start guide, deal stage definitions document | 4 | 8 | 6 |  |  |  |  | Deliverables: 1 admin guide, 1 end-user guide, 1 deal stage reference doc
Project Management | Kickoff, weekly status calls, project plan, stakeholder communication, change management | 10 | 16 | 13 |  |  |  |  | ~12% of total hours; assumes 6-8 week timeline; weekly 30-min syncs with Frank as primary contact
TOTAL
POST-PROJECT SUMMARY
Project Status:
Actual Start Date:
Actual End Date:
Actual Duration (weeks):
Scope Changes (count):
Change Order Value:
Overall Assessment:

## Risk Register
# | Risk | Severity | Likelihood | Impact | Mitigation | Owner | Status
1 | Scope Creep (Relationship Risk) | HIGH | HIGH | Close personal relationship (shared office, subleasing from Sayer) creates pressure for informal scope additions, free consultations, and "quick favors" that erode project boundaries and profitability | Define SOW boundaries explicitly; all work beyond SOW is change-ordered; set expectations upfront that professional relationship requires professional boundaries; document all verbal agreements | Consultant | Open
2 | FINRA Compliance Constraints | HIGH | MEDIUM | FINRA broker-dealer regulations may restrict email tracking pixels, data storage practices, or CRM feature usage; non-compliance could create regulatory liability for client | Recommend client review HubSpot configuration with compliance counsel before go-live; disable email open/click tracking by default until cleared; document all compliance-sensitive decisions; flag data residency for India-based EA access | Client (Jess/compliance) | Open
3 | Real Estate Pipeline Undefined | MEDIUM | HIGH | Real estate deal stages (Vijay/Philip parking garage pipeline) have not been discovered; scoping is based on assumed comparable complexity; actual requirements may significantly differ | Schedule discovery call with Vijay and Philip before implementation begins; scope real estate pipeline as contingent line item; adjust estimate after discovery | Client (Frank) + Consultant | Open
4 | Budget Gatekeeper Misalignment | MEDIUM | MEDIUM | Jess controls budget but was not in the detailed discovery call; Frank may commit to scope that Jess later rejects on cost; could delay or derail project after work begins | Ensure SOW is reviewed and signed by Jess/Brian (budget authority); present cost breakdown with clear ROI framing; include optional line items that can be removed to reduce cost | Client (Frank/Jess) | Open
5 | NDA Automation Limitations | MEDIUM | HIGH | Cameron discussed auto-attaching signed NDAs and auto-advancing deal stages, but without DocuSign or e-signature integration, this is manual; client may expect automated functionality that is not feasible | Clearly document that NDA tracking is manual (checkbox property) without e-signature tool; present DocuSign integration as future Phase 2 option; manage expectations in SOW | Consultant | Open
6 | Outlook Integration Quality | MEDIUM | MEDIUM | HubSpot Outlook integration has historically been less robust than Gmail; sidebar extension stability varies by M365 configuration; could frustrate users and hurt adoption | Test Outlook integration with client M365 environment during Week 1; validate sidebar, email logging, and calendar sync; have fallback plan (BCC forwarding) if extension is unstable | Consultant | Open
7 | Data Quality / Volume Unknown | LOW | MEDIUM | Contact volume not confirmed; Frank mentioned "10 key people" to start but categories span deal sourcing, vendors, LPs, lenders; actual volume could be significantly higher than estimated | Cap initial import scope at template-based upload; client populates template; if volume exceeds 1,000 contacts or requires multi-source merging, change order applies | Consultant + Client | Open
8 | Adoption Risk | LOW | LOW | Small team with Frank as champion reduces risk, but EA in India and real estate team may have different engagement levels; Jess described as "luddite" with technology | Frank as internal champion; keep initial build simple; role-specific training sessions; defer complex features to Phase 2 | Client (Frank) | Open

## Assumptions & Exclusions
SCOPE ASSUMPTIONS
1 | HubSpot Sales Hub Professional tier for full workflow automation capability
2 | 5 paid CRM seats (Frank, Pavel, Vijay, Philip, EA in India) + view-only access for Jess and Brian
3 | Microsoft 365 / Outlook as primary email and calendar platform for all users
4 | Up to 25 custom contact/company properties
5 | 2 deal pipelines: M&A (5 stages confirmed) and Real Estate (stages TBD)
6 | Up to 8 automated workflows
7 | 2-3 reporting dashboards with up to 8 custom reports
8 | Under 1,000 contacts for initial import via client-populated Excel template
9 | 1 test data load before final migration
10 | 6-8 week implementation timeline
11 | Single-phase rollout covering both pipelines, contacts, and reporting
12 | Frank C is primary point of contact and internal CRM champion
13 | No call recording or meeting transcription tools (FINRA compliance)
14 | NDA tracking is manual (checkbox property on deal record); no e-signature integration
15 | Adobe Acrobat used for PDF signing externally to HubSpot
OUT OF SCOPE
1 | Marketing Hub features or marketing automation (email campaigns, sequences, landing pages)
2 | Investor communications and LP management (recommended as Phase 2 after Jess/Brian discovery)
3 | DocuSign or e-signature integration
4 | Call recording or meeting transcription (Fireflies, Gong, etc.) due to FINRA compliance
5 | PitchBook or third-party data enrichment tools
6 | Detailed diligence tracking (remains in Excel per client preference)
7 | Project management functionality beyond basic deal review tracking properties
8 | Custom API development or middleware (n8n/Zapier)
9 | HubSpot Service Hub or Operations Hub features
10 | LinkedIn Sales Navigator integration
11 | Ongoing managed services beyond 2-week hypercare period
12 | FINRA compliance audit (client responsibility with their compliance counsel)
CLIENT RESPONSIBILITIES
1 | Populate contact import Excel template with accurate data by Week 2
2 | Provide deal stage definitions for Real Estate pipeline (Vijay/Philip) before pipeline build begins
3 | Procure HubSpot Sales Hub Professional licenses before implementation begins
4 | Designate Frank C as primary point of contact for decisions and approvals
5 | Ensure team availability for training sessions (M&A team, Real Estate team, EA)
6 | Review HubSpot configuration with FINRA compliance counsel before go-live
7 | Obtain SOW sign-off from budget authority (Jess/Brian)
8 | Provide M365 admin access for Outlook integration setup
9 | Complete UAT testing within agreed timeline
10 | Champion CRM adoption internally - Frank must set expectations for team usage
OPEN ITEMS
1 | Real estate pipeline stages - discovery call with Vijay and Philip required
2 | Investor comms / LP management requirements - discovery call with Jess and Brian required (Phase 2)
3 | Exact contact volume across all categories (deal sourcing, vendors, LPs, lenders)
4 | Target company list volume for company lifecycle stage tracking
5 | FINRA compliance review of HubSpot email tracking and data residency
6 | EA in India - specific CRM tasks and required access level
7 | Confirm budget authority sign-off process (Frank verbal vs. Jess/Brian written)
8 | HubSpot licensing negotiation timing and discount strategy

## Approach Comparison
Implementation Approach Comparison: Arkview Capital CRM
Dimension | Approach A: Single Phase (Recommended) | Approach B: Two-Phase Split
Description | All workstreams delivered in one phase: both pipelines, contacts, Outlook integration, reporting, training in single 6-8 week engagement | Phase 1 (Weeks 1-5): M&A pipeline + contacts + Outlook integration Phase 2 (Weeks 6-10): Real estate pipeline + additional reporting + optional marketing intro
Total Hours (Median) | ~121 hrs | ~131 hrs (+~10 hrs for duplicate PM, re-onboarding, context switching)
Timeline | 6-8 weeks | Phase 1: 5 weeks + Phase 2: 4-5 weeks = 9-10 weeks total
Risk Level | LOW-MEDIUM -- small team, straightforward scope, single engagement reduces context loss | LOW per phase but higher total risk from context switching and momentum loss between phases
Cost Efficiency | More efficient -- single kickoff, single UAT cycle, no re-onboarding | Less efficient -- duplicate PM overhead, second kickoff, risk of Phase 2 deprioritization
Adoption Impact | Team learns full system at once; Frank as champion can drive adoption across all features simultaneously | M&A team gets CRM first; real estate team waits, may lose interest or revert to Excel habits
Dependency Risk | Requires real estate pipeline discovery (Vijay/Philip) before project start | Can start Phase 1 immediately without real estate discovery; buys time for that conversation
Client Resource Demand | Moderate -- all discovery upfront, all training in one push; 5-person team makes scheduling manageable | Light per phase but spread over longer period; risk of stakeholder fatigue
Budget Sensitivity | Single invoice or milestone payments over 6-8 weeks; total investment visible upfront | Smaller Phase 1 invoice may be easier for Jess to approve; Phase 2 can be deferred if budget tightens
RECOMMENDATION
Single-phase approach (Approach A) is recommended for Arkview Capital, CONTINGENT on completing the real estate pipeline discovery call with Vijay and Philip before project kickoff. With only 5 users on a small fund team, the coordination overhead of a two-phase split outweighs the benefits. Frank is a strong internal champion who can drive simultaneous adoption across both pipelines. The single-phase approach also avoids the risk of Phase 2 deprioritization -- given Jess's cost sensitivity, there is a real chance Phase 2 never happens if Phase 1 doesn't immediately prove ROI. Building everything at once ensures the real estate team (Vijay/Philip) doesn't feel like second-class citizens and has CRM access from day one. HOWEVER: If the real estate discovery call cannot be scheduled within 2 weeks of SOW signing, fall back to Approach B to avoid blocking the M&A team. In that case, Phase 1 should include a placeholder real estate pipeline with generic stages that can be refined in Phase 2.