# The Milestone Group — HubSpot CRM Proposal

## A Note on This Proposal

Proposals are inherently a starting point—not a final blueprint. This document reflects our understanding of your challenges, a proposed solution, and the resources required to execute successfully.

We recognize that you, as the client, live with these challenges daily, and there may be details we have yet to uncover. Our goal is to use this as a conversation starter—to refine, align, and ensure we are solving the right problems in the right order.

If any aspect of the scope, solution, or pricing feels misaligned, let’s use that as a basis for further discussion.

## 1. Executive Summary

The Milestone Group is a national private equity real estate investment management firm with industry-leading returns since inception in 2003 and over $7 billion in real estate investments. With approximately 45 team members across offices in Dallas, Boca Raton, Atlanta, and a fourth location, Milestone manages apartment acquisitions across major U.S. metropolitan markets on behalf of leading institutional investors, pension funds, and sovereign wealth funds.

This proposal outlines a phased HubSpot CRM implementation designed to centralize contact and relationship management, capture deal activity, and replace fragmented tracking across Excel, OneNote, and individual email accounts. The engagement is structured as a three-phase rollout: Phase 1 delivers contact management and activity capture (weeks 1–4), Phase 2 introduces the deal pipeline (weeks 5–6), and Phase 3 adds integrations and advanced features (weeks 7–8+).

This phased approach is strongly recommended based on Milestone’s stated preference for starting simple and expanding. Team members range from 25 to 65 years old with varying technology comfort levels—a gradual rollout allows less technical users to build confidence with basic contact management before adding deal pipeline complexity. The previous DealCloud abandonment after two months underscores the adoption risk of an all-at-once approach. Phase 1 delivers immediate value with minimal behavior change, while Phases 2 and 3 build on established habits.

## 2. Objectives

Centralize contact and company data across all four offices into a single HubSpot CRM, replacing fragmented Excel, OneNote, and email-based tracking.

Configure relationship management for key personas—brokers, evangelists, investment partners, and lenders—with parent-child company associations for PE firm-to-portfolio company structures.

Capture and log all business development activity (calls, meetings, emails) automatically through Google Workspace and Fireflies integrations.

Build a structured deal pipeline with stage gates and qualification criteria to track opportunities from initial contact through close.

Deliver reporting dashboards that provide executive visibility into BD activity, contact engagement, and pipeline health.

Migrate and deduplicate 2,000–5,000 existing contacts from multiple sources into a clean, reliable CRM foundation.

Equip the team with training, documentation, and mobile access to drive adoption across all offices and age groups.

## 3. Scope of Work

Workstream 1: CRM Architecture & Setup

Customer Story: The Milestone Group wants a professionally configured HubSpot CRM environment that reflects their brand and supports their multi-office team structure with appropriate access controls.

Recommended Approach:

Configure HubSpot portal with Milestone branding and company settings

Set up user roles and permission sets for up to 10 users across 4 offices

Configure team structure aligned to office locations and functional roles

Establish naming conventions and organizational standards for long-term CRM hygiene

Configure security settings and data access controls appropriate for a PE firm

Assumptions:

Assumes HubSpot Sales Hub Starter or Smart CRM tier; final tier confirmed after scoping call

Up to 10 licensed CRM user seats

Portal configuration includes branding, default settings, and user provisioning

Workstream 2: Contact & Company Management

Customer Story: The Milestone Group wants to track relationships across brokers, evangelists, investment partners, lenders, and portfolio companies in a structured system that reflects the complexity of PE real estate relationship networks.

Recommended Approach:

Configure custom contact and company properties tailored to real estate PE workflows

Set up lifecycle stages for prospect-to-active relationship progression

Create association labels and parent-child company structures for PE firm-to-portfolio company relationships

Define and configure persona categories: broker, evangelist, investment partner, lender

Build segmentation lists for key contact categories and relationship types

Establish deduplication strategy and detection rules for ongoing data quality

Assumptions:

Includes up to 30 custom contact and company properties

Parent-child associations configured for PE firm-to-portfolio company structures

Persona tagging system for four primary relationship types

Deduplication rules configured for automated detection

Workstream 3: Data Migration — Contact Import

Customer Story: The Milestone Group wants to consolidate contacts currently scattered across Excel spreadsheets, OneNote, and individual email accounts into a single, clean CRM database.

Recommended Approach:

Audit existing contact data across all sources for volume, quality, and completeness

Develop field mapping between source data and HubSpot contact/company properties

Cleanse, standardize, and deduplicate contact records in a staging environment

Execute one test data load to validate mapping, formatting, and association accuracy

Perform final production import with post-migration validation and cleanup

Assumptions:

Assumes 2,000–5,000 contacts across 3–4 data sources

Moderate deduplication effort expected given multiple overlapping sources

One test load before final migration cutover

Client to provide complete contact exports from Excel, OneNote, and email by week 2

Does not include historical activity or deal data migration

Workstream 4: Email & Communication Setup

Customer Story: The Milestone Group wants seamless integration between their Google Workspace environment and HubSpot so that emails, meetings, and calendar activity are automatically captured in the CRM.

Recommended Approach:

Configure Google Workspace integration for Gmail and Google Calendar per user

Set up connected inbox configuration for each CRM user

Configure email tracking settings with appropriate opt-in preferences

Establish email domain exclusions to prevent logging of internal or irrelevant communications

Set up calendar sync for automatic meeting capture and logging

Assumptions:

Assumes Google Workspace as primary email and calendar platform

Per-user inbox connection and email tracking configuration

Includes email domain exclusion rules for internal communications

Calendar and contact sync configured across all active CRM users

Workstream 5: Automations & Workflows

Customer Story: The Milestone Group wants to reduce manual data entry and ensure consistent follow-up by automating activity capture, task reminders, and contact creation rules.

Recommended Approach:

Configure automated activity capture rules for emails and meetings

Build task reminder triggers for follow-up actions and overdue activities

Create follow-up workflows based on meeting outcomes and contact engagement

Set up automatic contact creation rules with appropriate filters

Configure email domain exclusions for auto-contact creation

Assumptions:

Includes up to 8 automated workflows

Covers activity capture automation, task reminders, and follow-up triggers

Auto-contact creation rules include email domain exclusions

Workflows will be documented for ongoing admin management

Workstream 6: Pipeline & Deal Management

Customer Story: The Milestone Group wants a structured deal pipeline to track investment opportunities from initial qualification through close, with stage gates that enforce data discipline.

Recommended Approach:

Build custom deal pipeline with stages aligned to Milestone’s investment process

Configure required fields per deal stage to enforce data completeness

Set up qualification criteria and stage gate enforcement

Create deal views and filters for team-based pipeline management

Configure deal properties for investment-specific data points

Assumptions:

Phase 2 deliverable (weeks 5–6); deal stages to be confirmed during scoping call

Assumes 1 primary pipeline with 4–6 stages

Includes required field enforcement per stage

Stage progression rules configured for data quality

Workstream 7: Integration — Fireflies

Customer Story: The Milestone Group wants meeting transcriptions from Fireflies to automatically log in HubSpot, reducing manual note-taking and ensuring institutional knowledge is captured in the CRM.

Recommended Approach:

Configure Fireflies-to-HubSpot native integration

Set up transcript mapping and activity logging rules

Configure contact matching logic to associate transcriptions with correct CRM records

Validate integration with sample meetings before go-live

Document known limitations and troubleshooting procedures

Assumptions:

Native Fireflies integration; no custom middleware required

Includes transcript mapping, contact matching, and activity logging configuration

Client must confirm Fireflies subscription with API access

Phase 3 deliverable (weeks 7–8+)

Workstream 8: Integration — Google Workspace

Customer Story: The Milestone Group wants calendar events, email communications, and contact data to sync bidirectionally between Google Workspace and HubSpot across all users.

Recommended Approach:

Configure calendar sync automation for all CRM users

Set up contact sync rules between Google Contacts and HubSpot

Establish sync frequency and conflict resolution rules

Validate sync accuracy and troubleshoot per-user configuration issues

Assumptions:

Scoped separately from email setup to cover calendar and contact sync automation

Assumes Google Workspace as the primary platform

Phase 3 deliverable (weeks 7–8+)

Includes per-user sync validation

Workstream 9: Reporting & Dashboards

Customer Story: The Milestone Group wants executive-level visibility into business development activity, contact engagement, and deal pipeline health through purpose-built dashboards.

Recommended Approach:

Build BD activity dashboard tracking calls, meetings, and emails by team member

Create contact overview dashboard with engagement metrics and lifecycle tracking

Configure deal pipeline dashboard with stage conversion and velocity metrics

Set up up to 10 custom reports across all dashboards

Configure report scheduling and email delivery for key stakeholders

Assumptions:

Includes 2–3 dashboards: BD activity, contact overview, deal pipeline

Up to 10 custom reports across all dashboards

Uses standard HubSpot reporting capabilities

Historical data available only from go-live date forward

Workstream 10: Training & Enablement

Customer Story: The Milestone Group wants their team—ranging from highly technical to less tech-savvy members across four offices—to be confident and competent using HubSpot in their daily workflows.

Recommended Approach:

Deliver 1–2 admin training sessions for designated power users covering settings, properties, workflows, and reporting

Deliver 2–3 end-user training sessions tailored to varying technical comfort levels

Cover daily CRM usage, mobile app setup, activity logging, and task management

Provide hands-on guidance for each office’s specific workflow patterns

Record sessions for future onboarding of new team members

Assumptions:

1–2 admin training sessions for 1–2 designated administrators

2–3 end-user sessions designed for varying tech comfort levels (ages 25–65)

Includes HubSpot mobile app setup and walkthrough

Sessions delivered virtually via screen share

Workstream 11: UAT, Go-Live & Documentation

Customer Story: The Milestone Group wants a controlled go-live process with testing, documentation, and post-launch support to ensure a smooth transition and sustained adoption.

Recommended Approach:

Develop test scripts for user acceptance testing across all configured workstreams

Conduct 2 UAT sessions with key stakeholders to validate configuration

Execute bug fix window for issues identified during testing

Create go-live cutover plan and checklist

Deliver process documentation: 1 admin guide, 1 end-user guide, 1 mobile quick-start guide

Provide 2-week hypercare support post-launch for issue resolution and adoption coaching

Assumptions:

Includes test script creation, 2 UAT sessions, and bug fix window

Go-live checklist and cutover plan included

Deliverables: 1 admin guide, 1 end-user guide, 1 mobile quick-start guide

2 weeks post-launch hypercare support included

Ongoing managed services beyond hypercare are not included

## 4. Deliverables & Milestones

Configured HubSpot CRM environment with Milestone branding and team structure

Contact and company management with persona tagging and parent-child associations

Data migration of 2,000–5,000 contacts from Excel, OneNote, and email sources

Google Workspace integration for email, calendar, and activity capture

Automated workflows for activity logging, task reminders, and follow-up

Deal pipeline with stage gates and qualification criteria

Fireflies integration for automated meeting transcription logging

Reporting dashboards for BD activity, contact engagement, and pipeline visibility

Admin and end-user training delivered across all offices

Documentation: admin guide, end-user guide, mobile quick-start guide

Estimated Timeline: 6–8 weeks

| Phase / Week Range | Scope Highlights |
| --- | --- |
| Phase 1: Weeks 1–4 | CRM architecture & setup, contact/company management, data migration, email & communication setup, automations & workflows |
| Phase 2: Weeks 5–6 | Deal pipeline configuration, stage gates, qualification criteria, pipeline reporting |
| Phase 3: Weeks 7–8+ | Fireflies integration, Google Workspace sync, advanced reporting, dashboard refinement |
| Go-Live: Weeks 6–8 | UAT testing, training sessions, documentation delivery, go-live cutover, 2-week hypercare support |

## 5. Engagement Model & Pricing

| Component | Model | Fee |
| --- | --- | --- |
| Project Delivery | Fixed Fee | $26,075 |

Model: Fixed Fee

Total Cost: $26,075

Project Timeline: 6–8 weeks

Payment Terms:

50% ($13,037.50) invoiced at project start

50% ($13,037.50) invoiced at final handoff (~Week 6–8)

Net-15 terms on all invoices

Technology & Administrative Fee: To help offset the costs of our technology stack and internal systems that improve project speed, quality, and efficiency, a 5% Technology & Administrative fee is applied to each invoice.

## 6. Project Governance

Sayer Responsibilities

Lead configuration, QA, and implementation across all workstreams

Conduct weekly check-ins and milestone reviews

Provide documentation, training, and go-live support

Manage project timeline and proactively communicate risks or blockers

The Milestone Group Responsibilities

Provide complete contact exports from Excel, OneNote, and email by week 2

Designate 1 primary point of contact for decisions and approvals

Ensure stakeholder availability for discovery, UAT, and training sessions

Procure HubSpot licenses before implementation begins

Procure or confirm Fireflies.ai subscription with API access

Provide Google Workspace admin access for email/calendar integration setup

Champion CRM adoption internally—leadership must set expectations for usage

Complete UAT testing within agreed timeline

Communicate deal stages and qualification criteria during scoping call

## 7. Assumptions & Constraints

HubSpot Sales Hub Starter or Smart CRM tier (final tier confirmed after scoping call)

Up to 10 licensed CRM users across 4 offices

Google Workspace (Gmail + Google Calendar) as primary email/calendar platform

Up to 30 custom contact/company properties

1 deal pipeline with 4–6 stages (Phase 2)

Up to 8 automated workflows

2–3 reporting dashboards with up to 10 custom reports

2,000–5,000 contacts to migrate from 3–4 sources

Fireflies.ai as transcription tool (existing subscription)

6–8 week implementation timeline with phased rollout

All work will be conducted remotely unless otherwise agreed

Scope assumptions listed in each workstream define boundaries

Any scope changes require formal approval and may impact cost or timing

Out of Scope:

Salesforce, Zoho, or any CRM other than HubSpot

ERP or accounting system integration

Asana integration (recommended for future phase)

Advanced deal flow management beyond basic pipeline (e.g., deal scoring, weighted pipeline)

Custom API development or middleware (n8n/Zapier)

Marketing automation (email campaigns, sequences, landing pages)

DocuSign or e-signature integration

HubSpot Service Hub or Operations Hub features

Ongoing managed services beyond 2-week hypercare

Hardware procurement or IT infrastructure changes

## 8. Approval & Next Steps

Please confirm alignment on scope and structure so we can move forward with scheduling a formal kickoff and assigning your Sayer team.

If any scope areas, phasing, or pricing need to be adjusted to fit your needs, we welcome the conversation.

To move forward with this engagement:

Provide written approval of this proposal via email

Schedule project kickoff within 1–2 weeks of written approval

Upon written approval, Sayer will issue a Master Services Agreement (MSA) via DocuSign, with this Scope of Work included. Once the MSA is executed, Sayer will finalize the implementation plan and begin onboarding.