## Approach Comparison
STRIVE Global -- CRM Foundation: Approach Comparison
Dimension | Approach A: Foundation First | Approach B: Quick Wins First
Description | Data cleanup and contact classification first (weeks 1-4), then pipeline restructuring and dashboards (weeks 5-8). Build on clean foundation. | Pipeline restructuring and dashboards first (weeks 1-4), then data cleanup and enrichment (weeks 5-8). Deliver visible wins early.
Total Hours (Median) | 119 hrs | 119 hrs
Timeline | 6-8 weeks | 6-8 weeks
Risk Level | LOW -- clean data enables accurate dashboards from day one | MEDIUM -- dashboards built on dirty data may show misleading metrics initially
Adoption Impact | Slower initial visibility but higher trust in data when dashboards launch | Faster dashboard delivery but reps may distrust inaccurate early reports
Change Management | Gradual -- team sees data improving before process changes | Immediate -- team gets new pipeline and dashboards right away
Dependency Risk | LOW -- data cleanup is independent of other workstreams | MEDIUM -- dashboards depend on data quality for accuracy
Client Resource Demand | Higher upfront (contact exports, classification rules, validation) | Lower upfront but higher mid-project for data cleanup
Board Reporting Value | Clean, trustworthy reports available by week 6 | Reports available by week 4 but accuracy improves through week 8
Cost | $17,850 (median at $150/hr) | $17,850 (median at $150/hr)
Recommendation
Approach A: Foundation First is recommended. STRIVE has 10 years of uncoded contact data and unreliable pipeline metrics. Building dashboards on dirty data risks eroding trust in the CRM before it has a chance to prove value. Clean the data first, then deliver dashboards that the team and board can trust from day one. This also aligns with Jodi's emphasis on building a strong data infrastructure as the foundation for future AI capabilities.

## Scoping Estimate
Hourly Rate: | 150
Workstream | Description | Min Hours | Max Hours | Median Hours | Rate | Min Cost | Max Cost | Median Cost | Notes / Assumptions | Actual Hours | Actual Cost | Variance
CRM Architecture & Config Review | Portal audit, user roles/permissions, team structure reconfiguration for existing Enterprise instance | 6 | 12 | [5 empty] | Assumes existing HubSpot Sales Hub Enterprise. Up to 23 seat users across sales, core, and service.
Pipeline Restructuring | Separate pre-pipeline from active pipeline. Partner-level vs. client-level deal categories. Stage probability mapping (5/20/40/50/60/80/90/100). Required fields per stage. Add Contracting stage. | 10 | 18 | [5 empty] | Two deal categories (partner, client) in same pipeline. Pre-pipeline as separate pipeline or board. Jodi's probability framework as starting point.
Contact & Company Classification + Cleanup | Contact type taxonomy (client/prospect/broker/partner). AI enrichment using HubSpot Breeze credits. Normalization, deduplication, association fixes. | 14 | 24 | [5 empty] | 10 years of uncoded data. +30-50% data quality premium applied. Includes pilot enrichment on 500 records. Assumes up to 30 custom properties.
Deal Health Scoring & Forecasting | Deal score based on stage + time-in-stage + activity recency. Healthy/at-risk/stale classification. Standardized close won/lost reasons (replace free-form with categorized dropdowns). | 6 | 12 | [5 empty] | Scoring formula and thresholds defined collaboratively with Andrea and Jodi.
Reporting & Dashboards | Partner dashboard (clonable with quick filters). Seller-specific KPI dashboard. CEO/board dashboard (sales revenue, new business, pipeline health). Up to 12 custom reports. | 10 | 18 | [5 empty] | Includes: open deals, pipeline value, avg deals/week, closed-won revenue, loss reasons, avg deal size, avg term length, appointments, contacts added.
Automations & Workflows | Fix Outlook email logging issue. Lead source tracking automation. Form-to-CRM for microsite client capture. Deal stage-change notifications. Duplicate protection rules. | 8 | 16 | [5 empty] | Up to 8 automated workflows. Outlook fix may require HubSpot support ticket if platform bug.
Email & Communication Fix | Outlook integration audit and fix. Email association rules to prevent logging to all related deals. Domain exclusions for internal communications. | 4 | 8 | [5 empty] | Root cause diagnosis in week 1. If config fix: 2-4 hrs. If platform bug: HubSpot support escalation.
Training: Admin | Andrea + designated admin. Pipeline management, reporting, workflow administration, data hygiene practices, enrichment tool usage. | 4 | 8 | [5 empty] | 1-2 sessions. Includes recorded walkthrough for future reference.
Training: End Users | Sales team. Daily CRM usage, deal entry, activity logging, dashboard consumption, mobile app setup. | 6 | 10 | [5 empty] | 2-3 sessions. Tailored to current team size and workflow.
Training: Executive | Jodi. Board dashboard walkthrough, forecast consumption, report scheduling, export for board decks. | 2 | 4 | [5 empty] | 1 session. Focused on CEO dashboard and board reporting.
UAT, Go-Live & Documentation | Test scripts, 2 UAT sessions with key stakeholders, bug fix window, go-live cutover plan. Deliverables: 1 admin guide, 1 user guide. 2-week hypercare post-launch. | 6 | 10 | [5 empty] | Hypercare includes issue resolution and adoption coaching.
Project Management | Kickoff, weekly syncs, status updates, change management, milestone reviews. | 10 | 16 | [5 empty] | ~12% of total estimated hours.
TOTAL

## Risk Register
# | Risk | Severity | Likelihood | Impact | Mitigation | Owner | Status
1 | 10 years of uncoded contact data -- AI enrichment scope may exceed estimates | HIGH | HIGH | Data cleanup takes 2-3x estimate; marketing segmentation delayed; project timeline extends | Run AI enrichment pilot on 500 records first. Measure classification accuracy before committing to full database run. Budget 30% buffer. | Consultant + Andrea | Open
2 | Pipeline under-reporting -- reps using LinkedIn and manual quoting outside CRM | HIGH | HIGH | Forecasting unreliable during transition; board sees pipeline dip before improvement | Jodi mandates CRM usage pre-launch. Set data entry expectations. Brief board that reported pipeline will increase as capture improves (not because business grew). | Jodi (executive sponsor) | Open
3 | Scope creep from close business relationship (shared office, referrals) | HIGH | MEDIUM | Informal requests bypass SOW; hours consumed without authorization; budget overrun | SOW signed by budget authority. All change requests documented formally. Weekly hours tracking visible to client. | Consultant + Jodi | Open
4 | Board ROI expectations -- if narrative overpromises, credibility risk | HIGH | MEDIUM | Board approves but expects unrealistic timeline or savings; sets up failure | ROI narrative uses conservative estimates with ranges, not point values. Tie ROI to measurable KPIs with 90-day check-in. | Consultant + Jodi | Open
5 | Seat/license confusion -- mixed versions across users, potential unused seats | MEDIUM | HIGH | Paying for unused seats; features expected but unavailable on current tier | Complete license audit in week 1. Produce cost savings memo before any configuration work. | Consultant + Jodi | Open
6 | Adoption risk -- sales reps prefer LinkedIn Sales Navigator over CRM | MEDIUM | HIGH | New CRM configuration goes unused; ROI unrealized; board investment wasted | Executive mandate from Jodi. Make CRM easier than alternatives (mobile, one-click logging). Rep-level dashboards show their own metrics. | Jodi + Andrea | Open
7 | Outlook email logging defect -- emails logging to all associated deals | LOW | MEDIUM | Fix may require HubSpot support escalation with unknown timeline; workaround needed in interim | Diagnose root cause in week 1. If platform bug, open HubSpot support ticket immediately and track SLA. | Consultant | Open
8 | COO identity ambiguity -- Lauren vs. Zach Beegal referenced in different calls | LOW | LOW | Miscommunication on stakeholder authority; NDA or admin access granted to wrong person | Clarify org chart and who controls HubSpot admin access during kickoff. | Consultant | Open

## Assumptions & Exclusions
Scope Assumptions
1 | HubSpot Sales Hub Enterprise (existing instance -- reconfiguration, not net-new setup)
2 | Up to 23 licensed users across 3 core, 10 sales, and 10 service seats
3 | Outlook as primary email platform (with known logging defect to be resolved)
4 | Up to 30 custom contact/company properties
5 | 1 active sales pipeline with pre-pipeline separated (new pipeline or board view)
6 | 2 deal categories: partner-level and client-level (same stages, different segmentation)
7 | Stage probability mapping using Jodi's framework as starting point (5/20/40/50/60/80/90/100)
8 | Contact type classification: client, prospect, broker, partner
9 | AI enrichment using HubSpot Breeze credits (5-10K credits available)
10 | Up to 8 automated workflows
11 | 3-4 reporting dashboards with up to 12 custom reports
12 | 6-8 week implementation timeline
13 | All work conducted remotely unless otherwise agreed
14 | Any scope changes managed through formal change request and may impact cost or timing
Out of Scope
1 | CPQ / quoting / product library build (see Option B: Full CRM Overhaul)
2 | Email sequencing or sales cadence automation
3 | Marketing automation (newsletters, campaigns, landing pages)
4 | NetSuite, Bill.com, or any ERP/financial system integration
5 | Client Success pipeline or client health scoring
6 | Commission tracking or calculation automation
7 | Contract management or e-signature workflows
8 | Custom API development or middleware (n8n/Zapier)
9 | Data migration from external systems (scope covers HubSpot internal cleanup only)
10 | Ongoing managed services beyond 2-week hypercare
11 | HubSpot license procurement or tier changes
12 | Hardware, IT infrastructure, or network changes
Client Responsibilities
1 | Designate primary point of contact for decisions and approvals (Andrea recommended)
2 | Ensure Jodi and Andrea availability for discovery, UAT, and training sessions
3 | Provide contact classification rules and validation for AI enrichment results
4 | Confirm deal stage definitions and probability framework before pipeline build
5 | Communicate standardized close won/lost reason categories
6 | Mandate CRM usage across sales team (executive sponsorship from Jodi)
7 | Complete UAT testing within agreed timeline
8 | Provide access to HubSpot admin portal
9 | Share 3-5 recent quotes/proposals for quoting workflow reference
Open Items
1 | Exact contact/company/deal record counts in HubSpot (pending portal access)
2 | Service Hub usage details -- who uses it, preserve or deprecate?
3 | COO identity and HubSpot admin access ownership (Lauren vs. Zach Beegal)
4 | Outlook email logging defect root cause (config vs. platform bug)
5 | Existing workflow inventory beyond broker trial form
6 | Historical deal data reliability for probability calibration
7 | Microsite client intake form link from Andrea
8 | Jodi's Wagmo stage naming framework (if available)
9 | SOW signing authority (Jodi as CEO or board approval required)