## Approach Comparison
STRIVE Global -- Full CRM Overhaul V2: Approach Comparison
Dimension | Approach A: Phased (Recommended) | Approach B: Concurrent
Description | Phase 1: CRM Foundation (weeks 1-8) -- pipeline, contacts, dashboards, automations. Phase 2: CPQ, enrichment, integrations, marketing (weeks 9-18). Each phase delivers standalone value. | All workstreams in parallel across 12-14 weeks. Maximum resource intensity.
Total Hours (Median) | 313 hrs across two phases | 313 hrs compressed
Timeline | 16-18 weeks (Phase 1: 8-10 wks + Phase 2: 8-10 wks) | 12-14 weeks
Risk Level | LOW -- Phase 1 de-risks Phase 2; clean data enables CPQ accuracy | HIGH -- dirty data undermines CPQ and reporting; multiple moving parts
Adoption Impact | Team absorbs changes gradually; builds confidence before CPQ launch | All-at-once change; higher cognitive load
Change Management | Two training cycles; Phase 1 habits established before Phase 2 | Single push covering all features
Dependency Risk | LOW -- Phase 2 depends on Phase 1, but Phase 1 is self-contained | HIGH -- CPQ depends on clean pipeline AND contact data simultaneously
Client Resource Demand | Spread over 18 weeks; manageable alongside day-to-day | Concentrated in 14 weeks; significant time commitment
Board Reporting Value | Phase 1 dashboards by week 8; full CPQ and advanced reporting by week 18 | Full suite by week 14 if everything goes to plan
Cost | $46,950 (median at $150/hr) | $46,950 (median at $150/hr)
Budget Flexibility | Can pause after Phase 1 ($23,250) if budget constrained | Full commitment required upfront
Recommendation
Approach A: Phased is strongly recommended. STRIVE's data quality issues make concurrent approach risky -- CPQ built on dirty data produces inaccurate quotes. Phase 1 delivers immediate operational value and can stand alone if Phase 2 is deferred. Estimates calibrated against prior comparable Salesforce engagement and HubSpot industry benchmarks (CPQ: 40-60 hrs industry standard).

## Scoping Estimate
Hourly Rate: | 150
Workstream | Description | Min Hours | Max Hours | Median Hours | Rate | Min Cost | Max Cost | Median Cost | Notes / Assumptions | Actual Hours | Actual Cost | Variance
PHASE 1: CRM FOUNDATION (Weeks 1-8)
CRM Architecture & Config Review | Portal audit, user roles, permissions, team structure, 3-hub assessment, seat review. | 8 | 16 | [5 empty] | Wagmo comparable: 14 hrs. HubSpot simpler but Enterprise 3-hub complexity.
Pipeline Restructuring | Pre-pipeline separation, partner/client categories, stage probabilities, required fields, Contracting stage, auto-transitions, deal age reset. | 16 | 32 | [5 empty] | Wagmo benchmark: 36 hrs SFDC pipeline. HubSpot -20%, Strive complexity +40%.
Contact & Company Classification + Cleanup | Contact taxonomy, AI enrichment pilot + full run, normalization, dedup, association fixes, duplicate protection. | 16 | 32 | [5 empty] | 10 yrs uncoded data. Industry: $5K-$15K for cleanup. Conservative with AI.
Deal Health Scoring & Forecasting | Deal score formula, healthy/at-risk/stale, standardized close reasons, forecasting views. | 6 | 14 | [5 empty] | Scoring defined collaboratively.
Reporting & Dashboards | Partner, seller, CEO/board, pipeline health dashboards. 15 custom reports. Scheduled exports. | 14 | 26 | [5 empty] | Wagmo: 20 hrs for simpler scope. Strive needs 4 dashboards + 15 reports.
Automations & Workflows | Outlook fix, lead source, form-to-CRM, stage notifications, dup protection, pre-pipeline transitions. | 10 | 18 | [5 empty] | Up to 10 workflows.
Email & Communication Fix | Outlook audit/fix, association rules, domain exclusions. | 4 | 8 | [5 empty] | Root cause week 1.
Training: Admin | Andrea + admin. Pipeline, reporting, workflows, data hygiene. | 4 | 8 | [5 empty] | 1-2 sessions recorded.
Training: End Users | Sales team. CRM usage, deals, activity, dashboards, mobile. | 6 | 10 | [5 empty] | 2-3 sessions.
Training: Executive | Jodi. Board dashboard, forecasting, scheduling. | 2 | 4 | [5 empty] | 1 session.
UAT, Go-Live & Documentation (Phase 1) | Test scripts, 2 UAT sessions, bug fixes, admin + user guide, 2-week hypercare. | 8 | 12 | [5 empty] | Wagmo testing: 7 hrs + documentation.
Project Management (Phase 1) | Kickoff, weekly syncs, status updates, scope control. | 14 | 22 | [5 empty] | ~12% of total. Wagmo lesson: formal PM prevents scope creep.
Phase 1 Subtotal
PHASE 2: CPQ, ENRICHMENT & INTEGRATIONS (Weeks 9-18)
CPQ Implementation | Product library (apps, microsites, AI, packs, Divi, bundles). Quote templates. E-signatures. Reminders. Multiple pricing models (license+rev share, flat, bundles/discounts). | 35 | 55 | [5 empty] | Industry benchmark: 40-60 hrs for CPQ rollout (Process Pro Consulting). Multiple pricing models add complexity. V1 was 18 hrs -- significantly under-scoped.
Contract Management Workflows | Quote-to-contract automation. Status tracking. Renewal/expiry workflows. Replaces manual DocuSign through COO. | 8 | 14 | [5 empty] | Contract templates, status properties, auto-advance on signature.
Data Enrichment at Scale | Full database Breeze AI enrichment. Auto-enrichment for inbound. QA and validation. | 8 | 16 | [5 empty] | Extends Phase 1 pilot to full database. Includes QA cycle.
Data Normalization & Dedup (Extended) | Full normalization, advanced dedup, merge strategy, ongoing protection. | 10 | 18 | [5 empty] | Extends Phase 1 cleanup comprehensively.
Parent-Child Structure (Broker Packs) | Association labels, per-broker forms, auto child contact creation, list generation. | 6 | 10 | [5 empty] | Enables microsite-to-app expansion. Depends on form link from Andrea.
Email Sequencing | Broker prospecting, microsite-to-app expansion. 4 sequences + enrollment + reporting. | 6 | 10 | [5 empty] | HubSpot Enterprise sequences included in license.
Marketing Automation Foundation | Newsletter template, 2-3 segmented campaigns, compliance. | 8 | 14 | [5 empty] | Leverages Marketing Hub (already licensed).
Commission Visibility & Validation | CRM-based commission view, validation workflow for Jodi. | 4 | 8 | [5 empty] | Visibility only -- not full calculation engine.
NetSuite Integration Prep | Data readiness, field mapping, gap analysis. PREP ONLY. | 8 | 14 | [5 empty] | Does NOT include API build. Separate SOW required.
Bill.com Integration Prep | AR/AP field mapping, data readiness. PREP ONLY. | 4 | 8 | [5 empty] | Does NOT include build. Separate SOW.
Seat/License Optimization | Audit 23 seats, identify waste, cost savings memo. | 2 | 4 | [5 empty] | Deliverable: cost savings recommendation.
Advanced Reporting | Automated board reports, pipeline coverage, pace-to-goal, marketing ROI. | 8 | 14 | [5 empty] | Extends Phase 1 dashboards with Phase 2 data.
Additional Project Management | Phase 2 PM, weekly syncs, milestone reviews. | 12 | 20 | [5 empty] | ~12% of Phase 2 hours.
Phase 2 Subtotal
OPTIONAL ADD-ON
Client Success Pipeline (Optional) | Client health tracking, health score properties, renewal tracking. Requires CS team discovery. | 8 | 14 | [5 empty] | Not in project total. Requires separate CS discovery.
PROJECT TOTAL (Phase 1 + Phase 2)

## Risk Register
# | Risk | Severity | Likelihood | Impact | Mitigation | Owner | Status
1 | 10 years uncoded contact data -- enrichment may exceed estimates | HIGH | HIGH | Cleanup 2-3x estimate; CPQ associations unreliable | Pilot 500 records in Phase 1. Budget 30% buffer. | Consultant + Andrea | Open
2 | Pipeline under-reporting -- reps on LinkedIn | HIGH | HIGH | Forecast unreliable; CPQ adoption depends on deal entry | Jodi mandates CRM usage. Board briefed on pipeline increase. | Jodi | Open
3 | Scope creep from close relationship | HIGH | MEDIUM | Informal requests; budget overrun on 18-week engagement | Formal SOW. Weekly hours tracking. Change request process. | Consultant + Jodi | Open
4 | Board ROI expectations | HIGH | MEDIUM | Unrealistic timeline expectations | Conservative ranges. 90-day check-in after Phase 1. | Consultant + Jodi | Open
5 | CPQ product library complexity | MEDIUM | HIGH | HubSpot CPQ may not handle all pricing models natively | Audit 5 recent quotes before build. Confirm Enterprise CPQ handles rev share. | Consultant | Open
6 | Seat/license confusion | MEDIUM | HIGH | Paying for unused seats; CPQ may need specific seats | License audit week 1. Cost savings memo. | Consultant + Jodi | Open
7 | NetSuite/Bill.com scope bleed | MEDIUM | MEDIUM | Prep becomes build without budget | Explicit boundary: prep only. Build = separate SOW. | Consultant | Open
8 | Adoption risk | MEDIUM | HIGH | CRM + CPQ unused; ROI unrealized | Executive mandate. Rep dashboards. Sequences reduce manual work. | Jodi + Andrea | Open
9 | Outlook email logging defect | LOW | MEDIUM | HubSpot support escalation timeline | Diagnose week 1. Open ticket if needed. | Consultant | Open
10 | COO ambiguity | LOW | LOW | Admin access issues | Clarify at kickoff. | Consultant | Open

## Assumptions & Exclusions
Scope Assumptions
1 | HubSpot Sales Hub Enterprise (existing instance -- reconfiguration)
2 | Up to 23 licensed users across core, sales, and service seats
3 | Outlook as primary email platform
4 | Up to 40 custom properties (expanded for CPQ and enrichment)
5 | 1 active sales pipeline with pre-pipeline separated
6 | 2 deal categories: partner-level and client-level
7 | Stage probability mapping using Jodi's framework
8 | AI enrichment using HubSpot Breeze credits (5-10K)
9 | Up to 12 automated workflows
10 | 4-5 dashboards with up to 20 custom reports
11 | Complete product/pricing inventory provided before CPQ build
12 | CPQ hours based on industry benchmark of 40-60 hrs (Process Pro Consulting)
13 | Marketing Hub leveraged for campaigns (already licensed)
14 | 16-18 week phased timeline
15 | Phase 1 can stand alone if Phase 2 deferred
16 | Estimates calibrated against prior Salesforce engagement and industry benchmarks
17 | All work conducted remotely
18 | Scope changes via formal change request
Out of Scope
1 | NetSuite integration build (prep only)
2 | Bill.com integration build (prep only)
3 | Client Success pipeline (optional add-on)
4 | Full commission calculation engine
5 | Custom API development beyond HubSpot native
6 | Other CRMs
7 | External data migration
8 | Managed services beyond hypercare per phase
9 | License procurement
10 | AI knowledge assistant
11 | LinkedIn Navigator integration
Client Responsibilities
1 | Designate primary POC (Andrea)
2 | Jodi + Andrea availability for sessions
3 | Complete product/pricing inventory before Phase 2 CPQ
4 | Contact classification rules and enrichment validation
5 | Deal stage definitions and probability framework
6 | Close won/lost reason categories
7 | Mandate CRM usage (Jodi exec sponsorship)
8 | Share 3-5 recent quotes across deal types
9 | UAT testing per phase
10 | HubSpot admin access
11 | NetSuite admin contact for integration prep
12 | Commission validation requirements
Open Items
1 | Contact/company/deal record counts (pending access)
2 | Product/pricing inventory for CPQ
3 | Service Hub usage
4 | COO identity and admin access
5 | Outlook defect root cause
6 | Existing workflow inventory
7 | Historical deal data reliability
8 | Microsite form link
9 | NetSuite entity structure
10 | SOW signing authority
11 | Divi positioning