## Trialta 6-Week Plan
Task | Min (hrs) | Max (hrs) | Est. Hours | Week | Notes / Dependencies
WEEK 1: Kickoff & CRM Foundation
Internal prep (review scope, prep agenda, build data template) | 1 | 2 | 1.5 | W1
Kickoff call with Trialta (Austin, Sam, Blake) | 0.75 | 1.5 | 1.125 | W1 | Align on timeline, roles, data expectations
Document decisions & send data import template | 0.5 | 1 | 0.75 | W1 | Team begins filling template this week
Configure HubSpot environment & Trialta branding | 0.5 | 1.5 | 1 | W1
Build contact properties (role, PE affiliation, strength) | 1 | 2 | 1.5 | W1 | Up to 20 custom properties
Build company properties & PE firm record types | 1 | 2 | 1.5 | W1 | PE firms = primary, portfolio cos = related
Configure contact/company associations & labels | 1 | 2 | 1.5 | W1 | PE firm → Portfolio company mapping
Week 1 Subtotal | 5.75 | 12 | 8.875
✓ Milestone: CRM structure built, data template with client |  |  |  | W1
WEEK 2: Outlook Integration & Begin Data Prep
Create segmentation views (PE vs sell-side vs portco) | 0.5 | 1.5 | 1 | W2
Set up Outlook integration for 3 users | 1 | 2 | 1.5 | W2 | Austin, Sam, Blake — Office 365
Test email sync, meeting sync, auto-contact creation | 0.5 | 1.5 | 1 | W2
Outlook training & enablement (30-min session) | 0.5 | 1 | 0.75 | W2 | Get team using CRM immediately
Receive & audit raw data files from team | 0.5 | 1.5 | 1 | W2 | DEPENDENCY: Team submits data by end of W2
Build import mapping (contacts, companies, deals) | 1.5 | 3 | 2.25 | W2 | Map their spreadsheet columns → HubSpot properties
Week 2 Subtotal | 4.5 | 10.5 | 7.5
✓ Milestone: Outlook live, data mapping complete |  |  |  | W2
WEEK 3: Data Migration & Cleanup
Clean & deduplicate contact records | 3 | 6 | 4.5 | W3 | RISK: Biggest variable. 500–1K contacts across 3 lists
Clean & map company records | 1.5 | 3 | 2.25 | W3 | Parallel with contact cleanup
Import contacts & companies into HubSpot | 1.5 | 3 | 2.25 | W3
Build PE firm → portfolio company associations | 1.5 | 3 | 2.25 | W3 | Manual association work post-import
Import historical deal records with PE attribution | 2 | 4 | 3 | W3
Assign contact/deal ownership (Austin/Sam/Blake) | 0.5 | 1.5 | 1 | W3
Week 3 Subtotal | 10 | 20.5 | 15.25
✓ Milestone: All historical data imported |  |  |  | W3
WEEK 4: Data QA & Deal Pipelines
Post-import QA & validation | 1.5 | 3 | 2.25 | W4 | Spot-check associations, dedup review
Team review & sign-off on imported data | 0.5 | 1 | 0.75 | W4 | Trialta confirms data accuracy — async or 30-min call
Configure buy-side pipeline & stages | 1 | 2 | 1.5 | W4 | Lead → Qualified → Proposal → Engaged → Completed
Configure sell-side pipeline & stages | 1 | 2 | 1.5 | W4
Build deal properties (engagement type, characteristics) | 1.5 | 3 | 2.25 | W4 | Up to 25 custom deal properties
Configure deal associations (PE firm, portco, contacts) | 1.5 | 3 | 2.25 | W4
Set up association labels & test with sample deals | 0.5 | 1.5 | 1 | W4
Pipeline walkthrough with team (30 min) | 0.5 | 1 | 0.75 | W4 | Quick demo, answer questions
Week 4 Subtotal | 8 | 16.5 | 12.25
✓ Milestone: Data validated, pipelines live & trained |  |  |  | W4
WEEK 5: Health Tracking & Reporting
Build PE firm health properties (last engagement, last contact) | 1.5 | 3 | 2.25 | W5
Configure "Days Since Last Engagement" calculated property | 1.5 | 3 | 2.25 | W5
Build PE firm views (active / warm / cold / dormant) | 1 | 2 | 1.5 | W5
Set up 90-day automated task creation | 1.5 | 3 | 2.25 | W5 | Auto-assign to PE firm relationship owner
Build saved filters for at-risk partnerships | 0.5 | 1.5 | 1 | W5
Build primary sales dashboard (~8 reports) | 3 | 5 | 4 | W5 | Pipeline velocity, PE sponsor value, engagement metrics
Build PE firm engagement health dashboard | 1.5 | 3 | 2.25 | W5
Configure deal conversion & pipeline reports | 1 | 2 | 1.5 | W5
Week 5 Subtotal | 11.5 | 22.5 | 17
✓ Milestone: Health tracking & dashboards live |  |  |  | W5
WEEK 6: QA, Enablement & Handoff
End-to-end UAT walkthrough | 1.5 | 3 | 2.25 | W6 | Test all workflows with real scenarios
Fix/adjust based on UAT feedback | 1.5 | 3 | 2.25 | W6 | Buffer for revisions & edge cases
Team enablement session (full system walkthrough) | 1 | 2 | 1.5 | W6 | 60–90 min live session — record it
Create quick-reference documentation | 1 | 2 | 1.5 | W6 | Daily CRM usage guide, key workflows
Formal handoff & begin 1-week async support | 0.5 | 1.5 | 1 | W6 | Slack/email support through W7
Week 6 Subtotal | 5.5 | 11.5 | 8.5
✓ Milestone: Project complete, team self-sufficient |  |  |  | W6
GRAND TOTAL | 45.25 | 93.5 | 69.375 | 6 wks | Est. Hours = median of min/max per task
Weekly Hours Summary
Week 1: Kickoff & CRM Foundation | 5.75 | 12 | 8.875
Week 2: Outlook & Data Prep | 4.5 | 10.5 | 7.5
Week 3: Data Migration | 10 | 20.5 | 15.25
Week 4: Data QA & Pipelines | 8 | 16.5 | 12.25
Week 5: Health Tracking & Reporting | 11.5 | 22.5 | 17
Week 6: QA & Handoff | 5.5 | 11.5 | 8.5
Avg Hours / Week | 7.5417 | 15.5833 | 11.5625